## Sheet1
Sr. No. | Module name | Status on 06-04.2020 | Solution | Action by | Expected Completion time | Completion date
1 | Call Creation | 1) There is no Provision to create calls for multiple sub job numbers at a time- Dotcom team claimed this point as extra but atleast 10 times we have asked this point with Dotcom developer and mentioned in all our observations. | It has to be done - Meanwhile User can create call for single sub job number at time | Dotcom | 4 days | To be discussed with Bipin
2 | Sub Job | 1) Sub/sub/job number is not working properly- Vaibhav and Rohini both are working on this point |  | Dotcom | 3 hours | 2020-04-12
|  | 2) Search is not working in listing page. - Vaibhav and Rohini both are working on this point | User need to put complete sub job number to search any data however Rohini and Vaibhav are working on this point . | Dotcom | 2 days
3 | Virtual call | 1) Needs to work on sequence of fields | Meanwhile user can use this module as it is. | Dotcom | 10 min
|  | 2) Remove compulsory fields from Virtual call creation page. | Needs to remove compulsory fields from Job number and sub job number fields | Dotcom | 10 min
|  | 3) Inspector name is not appearing in excel output , its showing some code in that column | User can use this module as its is meanwhile Vaibhav will clear this error. | Dotcom | 15 min
4 | Job number | 1) Format of reports field is also not working- user can't add Client format of report and other documents | Default format is available to create visit report | Dotcom | 30 min
|  | 2) Job number is not as per TUV format- One additonal Zero is appearing there | Meanwhile user can use this module as it is. | Dotcom | 15 min
|  | 3) Sequence of both pages.- Needs to set sequence of listing page | Meanwhile user can use this module as it is. | Dotcom | 30 min
5 | Inspector call page | 1) Format of reports are not appearing. | Default format of reports are available to create visit report | Dotcom | 30 min
|  | 2) Needs to work on multiple calls close option- Shrikant/ Sunil will explain this point | It has to be done All dates are not appearing in visit report | Dotcom | 4 days | To be discussed with Bipin
|  | 3) No option to view visit report created against call. - Dotcom team is claiming this point as extra but this point is working in our old system. | Meanwhile User can get reports in visit reports section | Dotcom | 3 hours
6 | Non inspection activity | 1) Its showing combined entry for multiple days - we need to create a separate entry for each day - This point was missed by TUV team at time of earlier observations. | It has to be done | Dotcom/TUV | 1 day
7 | Library | 1) Provide sort option in Folder page. | Meanwhile user can use this module as it is. | Dotcom
|  | 2) Check possibility to add Corporate communication section in library module. | Meanwhile user can use this module as it is wihtout corporate communication
|  | 3) Date of modification is n0t getting updated. | user can use library section meanwhile Vaibhav will clear this error
8 | MIS | Initial observations sent to Dotcom team but we can check these reports when actual project get live that time we will get atual data | Test cases to be created | TUV | 02 days | 2020-04-09
9 | Expenses | Checked till voucher creation and sent observations to Dotcom team and today morning they have cleared error- I will check next flow soon | Dotcom team will clear this point within next week | TUV | 01 day | 2020-04-09
10 | Training | Module developed by Dotcom team is not acceptable and at meeting with Manish sir , Bipin promised us to developed this module once project go live or at end of all modules. | Pending from Dotcom team | Dotcom | Will be completed after go live.
11 | NCR | Shrikant / Sunil will explain this module. | Completed | -
12 | Visit report | Shrikant / Sunil will explain this module. | 80% work completed | Dotcom |  | 2020-04-09
13 | IRN | Shrikant / Sunil will explain this module. | Development is completed - but previous observations are pending , they will complete these observations within this week | Dotcom |  | 2020-04-09
14 | Quotation | 1) Format of Communication protocol varies from quotation to quotation., needs to fix for all quotation - Dotcom team is claiming this point as extra point - From initial period we were against of this page and same conveyed to Dotcom team time to time , there is no option to save quotation at this stage, there are many fields like validity , address of Client etc fields are appearing at this stage and such fields are not available in first page Here user need to set alignment of whole quotation each time when he open quotation . Ms Rohini also asked Dotcom team many times about print preview option but still observations raised . | User can create quotation but user need to set aligment of whole quotation each time | Dotcom |  | 2020-04-14
|  | 2) Copy quotation is not working and not acceptable - I have checked copy quotation function and its not at all satisfactory . its not simplest way to copy quotation . after third observations from TUV Dotcom team has created this function and developed function does not fulfil our requirements , it is copying data of randomly selected quotation . | User can create quotation but without copying previsoin quotation | Dotcom |  | 2020-04-14
|  | 3- Validity fields - This field is hardcoded and now Dotcom team is claiming this point as extra but we never asked Dotcom team to keep this field as hardcoded. | It has to be done. | Dotcom
15 | NEWS section | 1)There is no option to update image, edit image | It has to be done
|  | 2)Not able to select” inactive” status of active News . | It has to be done