## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number | As Per Email Dtd.29.11.2022
Project Name & Location | NA
Client Name | Navin Fluorine International Ltd.
End User Name | Navin Fluorine International Ltd.
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name
PO Number (Client PO on Vendor)
Sub Vendor
PO Number (Vendor PO on Sub Vendor)
Inspection Location
Inspection Date(s)

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | E1214R004 | HSN/SAC CODE8419 E1214R Tube Bundle for E1526/E1214R Job No:22915 | number | 1 | 1 | --
2 | E1306R05 | HSN/SAC CODE8419 TUBE BUNDLE FOR E 1306R, JOB NO 2291601 & 02 | number | 2 | 2 | -- |  | number
3 | E1524006 | HSN/SAC CODE8419 TUBE BUNDLE FOR E1524, JOB NO 2291701 & 02 | number | 2 | 2 | --
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | Not Applicable | 22263 REV 1, 22264 REV 1, 22265 REV 1 | Approved by M/s.Tamilnadu Petroproducts Ltd.
3 | Drawing(s) | Not Applicable | UX184 REV 2 UX175 REV 4, UX176 REV 4 UX185 REV 1 | Approved by M/s.Tamilnadu Petroproducts Ltd.
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
QAP (22-263, 22-264, 22-265, Rev.01)Stage No.1.0.0(1.1.0 & 1.2.0) - Raw material identification for Tubes & forging of tubesheet- Found meet with material specification.
QAP (22-263, 22-264, 22-265, Rev.01)stage. No.2.2.0: Tube sheet dimensions (Hole size, ligament, pitch etc) witnessed Found as per drawing, found Satisfactory.
QAP (22-263, 22-264, 22-265, Rev.01)stage. No.2.3.0: Tube bundle Skelton dimensions & alignment witnessed Found as per drawing & found Satisfactory.
QAP (22-263, 22-264, 22-265, Rev.01)stage. No.2.4.0-(b): Pneumatic leak test witnessed @ 2 Kg/cm2-No any leakage observed during test. Found Satisfactory.
QAP (22-263, 22-264, 22-265, Rev.01)stage. No.3.0.0(3.1.1)-Witnessed Shell side Hydrostatic test for TTJ weld of Equipment - No leakage and no pressure drop observed during holding time.(Hydrotest performed with Dummy shell at higher side pressure for 1Hr holding time ).
QAP (22-263, 22-264, 22-265, Rev.01)stage. No.3.0.0(3.1.2)-Witnessed complete tube bundle overall dimension & orientation - Dimension found as per drawing & found satisfactory

## Document reviewed
Document reviewed
QAP (22-263, 22-264, 22-265, Rev.01)Stage No.1.0.0(1.1.0 & 1.2.0) - Reviewed material heat chart for pressure parts with MTC- Found in order.
QAP (22-263, 22-264, 22-265, Rev.01)Stage No.2.0.0(2.1.0 ) - Reviewed WPS, PQR as per ASME SEC IX - Found meet with as per code.
QAP (22-263, 22-264, 22-265, Rev.01)Stage no.2.4.0 (a)- Reviewed reports for DP test (Root & Final run) for tube to timesheet weld joint - Found in order.
QAP (22-263, 22-264, 22-265, Rev.01)Stage no.2.4.0 (c)- Reviewed Expansion report for tube to timesheet weld joint - Found in order.
Calibration certificates for measuring instruments used during inspection was reviewed / verified and found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
None
Identification of Inspected Item(s):
Oval Stamp
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Offered stage Inspection acceptance subjected to vendors action on points mentioned in areas of concern & satisfactory completion of pending activities as per QAP.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: