## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 010101145721/20
SAP number | 8118997801
Notification Number | DEM/-KPTL/BALL/SVITA/MECON/2021-22/04 Email Dated - 24.01.2022
Project Name & Location | North East Gas Grid (NEGG) Project - Part A
Client Name | Kalpataru Power Transmission Limited (31127)
End User Name | Indradhanush Gas Grid Limited (36014)
DEC / PMC / EPC Name | Mecon Ltd Delhi
DEC / PMC / EPC Number | Not Applicable
Vendor Name | DEMBLA VALVES LIMITED (38243)
PO Number (Client PO on Vendor) | 2300122188 Dated - 10.06.2021
Sub Vendor | Not Applicable
PO Number (Vendor PO on Sub Vendor) | Not Applicable
Inspection Location | A/8 Arham Logicpark Village - Valishind, Mumbai Nashik National Highway ( NH3 ) Taluka : Bhiwandi, District : Thane, State : Maharashtra - 421302
Inspection Date(s) | 27.01.2022, 28.01.2022, 29.01.2022 & 31.01.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BEC Size: DN 20 [3/4" ] X 150#, FE, RF MOC: ASTM A351 Gr CF8M (SS) Valve Sr no: 22V3179 10% Dimension Witnessed Valve Sr. No.: 22V3179 VIBA MTC No.: VFC/W157/126/2022 Dt. 24.08.2022 | number | 1 | 1 | 1 | 1 | number
2 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BED1 Size: DN 20 [3/4" ] X 150#, FE, RF MOC: ASTM A351 Gr CF3M (SS) Valve Sr no: 22V3180 To 22V3181 10% Dimension Witnessed Valve Sr. No.: 22V3181 VIBA MTC No.: VFC/W157/126/2022 Dt. 24.08.2022 | number | 2 | 2 | 2 | 2 | meter
3 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BBB Size: DN 25 [1" ] X 800#, Screwed to BSPT(F) Thread MOC: ASTM A105 (CS) Valve Sr no: 22V3182 To 22V3192 10% Dimension Witnessed Valve Sr. No.: 22V3186, 22V3191 VIBA MTC No.: VFC/W157/126/2022 Dt. 24.08.2022 | number | 11 | 11 | 11 | 11 | km
4 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BEC Size: DN 40 [1 1/2" ] X 150#, FE, RF MOC: ASTM A351 Gr CF8M (SS) Valve Sr no: 22V3193 10% Dimension Witnessed Valve Sr. No.: 22V3193 VIBA MTC No.: VFC/W157/126/2022 Dt. 24.08.2022 | number | 1 | 1 | 1 | 1 | meter (number)
5 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BED2 Size: DN 80 [3" ] X 150#, FE, RF MOC: ASTM A351 Gr CF3M (SS) Valve Sr no: 22V3146 To 22V3147 10% PMI Witnessed Valve Sr. No.: 22V3146 VIBA MTC No.: VFC/W157/123/2022 Dt. 23.08.2022 | number | 2 | 2 | 2 | 2 | km (number)
7 | NA | Hand wheel Operated Bolted Bonnet Gate Valve Piping Class: CBA Size: DN 40 [1 1/2" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3110 To 22V3111 10% Dimension Witnessed Valve Sr. No.: 22V3110 VIBA MTC No.: VFC/W157/118/2022 Dt. 16.08.2022 | number | 2 | 2 | 2 | 2 | each
8 | NA | Hand wheel Operated Bolted Bonnet Gate Valve Piping Class: CBA Size: DN 80 [3" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3112 To 22V3120 10% Dimension Witnessed Valve Sr. No.: 22V3117 VIBA MTC No.: VFC/W157/118/2022 Dt. 16.08.2022 | number | 9 | 9 | 9 | 9 | Piece
11 | NA | Swing Check Valve Piping Class: CBA Size: DN 150 [6" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3122 To 22V3124 10% Dimension Witnessed Valve Sr. No.: 22V3123 VIBA MTC No.: VFC/W157/119/2022 Dt. 16.08.2022 | number | 3 | 3 | 3 | 3 | Test sample
12 | NA | Hand wheel Operated Bolted Bonnet Globe Valve Piping Class: CBR Size: DN 15 [1/2" ] X 800#, SW MOC: ASTM A105 (CS) Valve Sr no: 22V3125 To 22V3127 10% Dimension Witnessed Valve Sr. No.: 22V3126 VIBA MTC No.: VFC/W157/119/2022 Dt. 16.08.2022 | number | 3 | 3 | 3 | 3 | AU - All Unit
2 | NA | Hand wheel Operated Bolted Bonnet Gate Valve Piping Class: BBC Size: DN 25 [1" ] X 800#, SW MOC: ASTM A105 (CS) Valve Sr no: 22V3106 To 22V3108 10% Dimension Witnessed Valve Sr. No.: 22V3107 VIBA MTC No.: VFC/W157/118/2022 Dt. 16.08.2022 | number | 3 | 3 | 3 | 3 | lot
3 | NA | Hand wheel Operated Bolted Bonnet Globe Valve Piping Class: BBC Size: DN 15 [1/2" ] X 800#, SW MOC: ASTM A105 (CS) Valve Sr no: 22V3109 Dimension Witnessed Valve Sr. No.: 22V3109 VIBA MTC No.: VFC/W157/118/2022 Dt. 16.08.2022 | number | 1 | 1 | 1 | 1 | Set
4 | NA | Lever Operated Ball Valve [2 Piece, FB] Piping Class: BBC Size: DN 50 [2" ] X 150#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3148 Dimension Witnessed Valve Sr. No.: 22V3148 VIBA MTC No.: VFC/W157/123/2022 Dt. 23.08.2022 | number | 1 | 1 | 1 | 1 | Running Meter
5 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BEA Size: DN 25 [1" ] X 150#, FE, RF MOC: ASTM A351 Gr CF8 (SS) Valve Sr no: 22V3142 To 22V3145 10% PMI Witnessed Valve Sr. No.: 22V3143 VIBA MTC No.: VFC/W157/123/2022 Dt. 23.08.2022 | number | 4 | 4 | 4 | 4 | kg
6 | NA | Lever Operated Ball Valve [3 Piece, FB] Piping Class: BEA Size: DN 80 [3" ] X 150#, FE, RF MOC: ASTM A351 Gr CF8 (SS) Valve Sr no: 22V3149 To 22V3151 10% PMI Witnessed Valve Sr. No.: 22V3150 VIBA MTC No.: VFC/W157/123/2022 Dt. 23.08.2022 | number | 3 | 3 | 3 | 3 | metric ton (tonne)
9 | NA | Gear Operated Bolted Bonnet Gate Valve Piping Class: CBA Size: DN 200 [8" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3121 Dimension Witnessed Valve Sr. No.: 22V3121 VIBA MTC No.: VFC/W157/119/2022 Dt. 16.08.2022 | number | 1 | 1 | 1 | 1 | ton
10 | NA | Swing Check Valve Piping Class: BBC Size: DN 100 [4" ] X 150#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3196 Dimension Witnessed Valve Sr. No.: 22V3196 VIBA MTC No.: VFC/W157/126/2022 Dt. 24.08.2022 | number | 1 | 1 | 1 | 1 | cubic millimetre
6 | NA | Hand wheel Operated Bolted Bonnet Gate Valve Piping Class: CBA Size: DN 25 [1" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3415 To 22V3418 10% Dimension Witnessed Valve Sr. No.: 22V3417 VIBA MTC No.: VFC/W157/145/2022 Dt. 24.08.2022 | number | 4 | 4 | 4 | 4 | cubic centimeter
7 | NA | Hand wheel Operated Bolted Bonnet Gate Valve Piping Class: CBA Size: DN 15 [1/2" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3419 To 22V3424 10% Dimension Witnessed Valve Sr. No.: 22V3424 VIBA MTC No.: VFC/W157/145/2022 Dt. 24.08.2022 | number | 6 | 6 | 6 | 6 | cubic meter
8 | NA | Hand wheel Operated Bolted Bonnet Gate Valve Piping Class: CBA Size: DN 25 [1" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3425 To 22V3438 10% Dimension Witnessed Valve Sr. No.: 22V3427, 22V3435 VIBA MTC No.: VFC/W157/145/2022 Dt. 24.08.2022 | number | 14 | 14 | 14 | 14 | cubic inch
13 | NA | Hand wheel Operated Bolted Bonnet Globe Valve Piping Class: CBR Size: DN 80 [3" ] X 300#, FE, RF MOC: ASTM A216 Gr WCB (CS) Valve Sr no: 22V3439 To 22V3442 10% Dimension Witnessed Valve Sr. No.: 22V3440 VIBA MTC No.: VFC/W157/145/2022 Dt. 24.08.2022 | number | 4 | 4 | 4 | 4 | cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | Not Applicable | QAP/22-23/011 Rev.00 | Approved With comment By VVF
3 | Drawing(s) | Not Applicable | 22W157-BLV-FL-CF8M-150-01 Rev.0 For PO Sr. No 1 & 4 (BEC) 22W157-BLV-FL-CF3M-150-02 Rev.0 For PO Sr. No 2 (BED 1) & 5 (BED2) 22W157-BLV-FL-CF8-150-15 Rev.0 For PO Sr. No 6 (BEA) 22W157-BLV-SC-A105-800-03 Rev.0 For PO Sr. No 3 (BBB) 22W157-BLV-FL-WCB-150-04 Rev.0 For PO Sr. No 4(BBC) 22W157-BLV-FL-CF8-150-05 Rev.0 For PO Sr. No 5 (BEA) 22W157-GTV-SW-A105-800-06 Rev.0 For PO Sr. No 2 (BBC) 22W157-GBV-SW-A105-800-07 Rev.0 For PO Sr. No 3 (BBC) & 12 (CBR) 22W157-GTV-FL-WCB-300-08 Rev.0 For PO Sr. No 7 (CBA) 22W157-GTV-FL-WCB-300-10 Rev.0 For PO Sr. No 8 (CBA) 22W157-GTV-FL-WCB-300-11 Rev.0 For PO Sr. No 9 (CBA) 22W157-SCV-FL-WCB-150-12 Rev.0 For PO Sr. No 10 (BBC) 22W157-SCV-FL-WCB-300-13 Rev.0 For PO Sr. No 11 (CBA) 22W157-GTV-FL-WCB-300-08 Rev.01 For PO Sr. No 6 & 8 (CBA) 22W157-GTV-FL-WCB-300-09 Rev.0 For PO Sr. No 7 (CBA) 22W157-GBV-FL-WCB-300-14 Rev.0 For PO Sr. No 13 (CBR) | Approved By VVF
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | VT-SPC-VVF-02 Rev.1 (Valve Specification) | Not Applicable | Provided By Client
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
QAP Stage No 2.1: Visual Checked for Surface( Outside & Inside feasible area ) condition, workmanship on 100% Qty. from offered each PO line Item- Found free from oil, grease, burr, Dent & obvious defects at the time of inspection
QAP Stage No 2.1: Dimension checked ( F-F, Bore, Flange OD, Thk, PCD, Hole dia, No of holes, RF etc) as per drawing on 10% randomly selected Qty. from offered each PO line Item -Found to meet QAP & approved drawing requirement.
QAP Stage No 2.1: Shell hydro test witnessed as per approved drawings & QAP on offered 100% qty from each PO line item –No leakage, No pressure drop observed during holding time.
QAP Stage No 2.1:- Back Seat hydro test (Gate & Globe Valve) witnessed as per approved drawings & QAP on offered 100% qty from each applicable PO line item –No leakage, No pressure drop observed during holding time.
QAP Stage No 2.1:- Seat hydro test witnessed as per approved drawings & QAP on offered 100% qty from each PO line item–No leakage, No pressure drop observed during holding time.
QAP Stage No 2.1: Seat Pneumatic test (Except Check Valve) witnessed as per approved drawings & QAP on offered 100% qty from each PO line item –No leakage, No pressure drop observed during holding time.
QAP Stage No 2.1: Operational & Functional test (Manually Open / Close) checked on 100% qty from offered each PO line item- Found smooth operation at the time of inspection
QAP Stage No 2.2: PMI test carried out on all accessible SS part (Body, Bonnet, Cover)-found to meet material specification & QAP requirement
All measuring Instruments/ Equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Stage No 1.1: Raw material test certificates as per EN 10204:3.1 for Body, Bonnet, cover declare by supplier on offered Qty. –Found to meet ITP & material specification requirement
QAP Stage No 1.2: Manufacturer/Lab test report as for Wedge/Plug/Disc, Spindle declare by supplier on offered qty–Found to meet ITP requirement.
QAP Stage No.2.5: Manufcaturer test certificates as per EN 10204:3.1 reviewed-Found to meet ITP & drawing requirement.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
PO Sr. No. 10 Valves provisionally hard stamped as " " for identification near manufacturer marking subjected to points mentioned in area of concrn column.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable subjected to manufacturer action on points mentioned in area of concern column.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: