## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number | Email Dt.22.12.2022
Project Name & Location | Not Applicable
Client Name | SchuF Speciality Valves India Private Limited
End User Name | SchuF Speciality Valves India Private Limited
DEC / PMC / EPC Name | Not Applicable
DEC / PMC / EPC Number | Not Applicable
Vendor Name | Arvind Pipes Fittings Industries
PO Number (Client PO on Vendor) | P108581 Rev.2 DT.09.11.2022
Sub Vendor | Not Applicable
PO Number (Vendor PO on Sub Vendor) | Not Applicable
Inspection Location | Plot Number,203, Siddhi Industrial Infra Park, MGVCL Waghodia, Vadodara
Inspection Date(s) | 23.12.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 1573738 | S.S. Seamless Pipe EN 10216-5 (1.4401/1.4404) / ASME SA 312/SA 312M TP 316/316L, 273 mm OD X 9.27mm W.T, ( Heat No. A-1912) | meter | 3 | 3.87 | 3.87 | 3.87 | number
2 | 1573746 | S.S. Seamless Pipe EN 10216-5 (1.4401/1.4404) / ASME SA 312/SA 312M TP 316/316L, 457.2 mm OD X 10 mm W.T ( Heat No. P-1410) | meter | 3 | 2.46 | 2.46 | 2.46 | meter
9 | 1577008 | S.S. Seamless Pipe EN 10216-5 (1.4404) / ASME SA 312/SA 312M TP 316L, 141.3 mm OD X 6.55mm W.T, PIPE( Heat No. A-2033) | meter | 6 | 5.66 | 5.66 | 5.66 | km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | Not Applicable | QAP/PIPE/SCHUF/21-22/01 REV.1 DT. 11.11.2022 | Approved by Client -SchuF
3 | Drawing(s) | Not Applicable | Not Applicable | Not Applicable
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
ITP Sr. No.1A - Product sample identified for Chemical & Mechanical test (Tensile, Impact at -196 Deg.C & Flattening test) and IGC PR “E” test samples identified by TUV – Found to meet applicable code, QAP and specification requirements.
ITP Sr. No.1C - Visual inspection carried out for 100% Qty. of offered lot - No injurious surface imperfections were observed.
ITP Sr. No.1C - Dimensional inspection carried out for 100% Qty. of offered lot - Found to meet the code and standard requirement.
All measuring instruments / equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found acceptable.

## Document reviewed
Document reviewed
ITP Sr. No.1A - Chemical check test lab report reviewed for its technical content only – Found to meet the applicable code and project specification requirement.
ITP Sr. No.1B - Hydrotest report reviewed - Found to meet applicable code & specification requirements.
ITP Sr. No.1C - Visual & Dimensional report reviewed - Found to meet applicable code & specification requirements.
Manufacturer's test certificate No. ARVIND/P/2022/1873 & ARVIND/P/2022/1874, Dtd: 04.01.2023 reviewed - Found to meet applicable code requirement.
All measuring instruments / equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found acceptable.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Measure Tape | 0-3000MM | MHS/WI/CL/00 | 09.08.2023 | MH/CL/22/08/363/NABL DT.10.08.2022 | Yes | No | Yes
2 | Vernier Caliper | 0-300mm | MHS/WI/CL/01 | 16.08.2023 | MH/CL/22/08/476/NABL DT.17.08.2022 | Yes | No | No
3 | Ultrasnic Thickness Gauge | 3 TO 100MM | MHS/WI/CL/08 | 13.08.2023 | MH/CL/22/08/369/NABL DT.12.08.2022 | Yes | No
4 | Dial Thickness Gauge | 0-10mm | MHS/WI/CL/34 | 09.08.2023 | MH/CL/22/08/069 DT.12.08.2022 | No | Yes

## Areas of concerns
Areas Of Concern
As per Purchase order dual certification required (EN 10216-5 & EN 10204 type 3.2). However inspection carried out under Third party by M/s Arvind Pipes Fittings Industries.

## Pending Activities
Pending Activities from this visit
None.

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
None
Identification of Inspected Item(s):
All Inspected items identified with Hard single stamped as “ “ near manufacturer marking.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable subject to pending activities.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: