## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 010101000720/63
SAP number | 8116951219
Notification Number | Email dtd 15.10.2021
Project Name & Location | DDP RIL HMD
Client Name | RELIANCE INDUSTRIES LTD.
End User Name | RELIANCE INDUSTRIES LTD.
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | HEM INDUSTRIES
PO Number (Client PO on Vendor) | MMH/240345345 - 15/02/2021
Sub Vendor
PO Number (Vendor PO on Sub Vendor)
Inspection Location | Silvassa,
Inspection Date(s) | 16.10.2021

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
5 | 2001570894 | STDBLT+N B7 2H 10UNC 0.750" 13.500" Mat spec, stud bolt(s): ASTM A193 GRADE B7 Mat spec, nut(s): ASTM A194 GRADE 2H Design spec, stud bolt: ASME B1.1 Design spec, nut: ASME B18.2.2 Thread class symbol, stud bolt 2A Thread class symbol, nut: 2B Type, thread: 10UNC Number, nuts per stud bolt: 2 Type, nut: HEAVY HEXAGONAL Size: 0.750 INCH Length: 13.500 INCH Drawing: RB 1547 REV A MANUFACTURER: ROTABOLT FITTED WITH ROTABOLT ,1 TENSION CONTROL LNDICATOR | each | 200 | 200 | 200 | 200 | number
6 | 2001140959 | SCREW HEX SCK ALN BLT CL10.9 MC 30MM M12 Mat: HIGH TENSILE CARBON STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: ISO 4762 CLASS 10.9 Type, thread: METRIC COARSE Length, thread mm 30 Length, under head mm 30 Size: M12 ,Metric Hexagon Socket Screws | each | 100 | 0 | 0 | 0 | meter
8 | 2001119869 | Metric Hexagon Socket Screws SCREW HEX SCK ALN BLT GR 12.9 70 MM M8 Mat: HIGH TENSILE STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: IS 1367 PART-III GRADE 12.9 Type, thread: METRIC COARSE Length, thread Size: M8,Metric Hexagon Socket Screws | each | 200 | 200 | 200 | 200 | km
9 | 2001119871 | SCREW HEX SCK ALN BLT GR12.9 MC 100MM M8 Mat: HIGH TENSILE STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: IS 1367 PART-III GRADE 12.9 Type, thread: METRIC COARSE Pitch, thread coarse: 1.25 Length, thread mm 100 Length, under head mm 100 Size, socket mm M8 Size: M8 | each | 200 | 200 | 200 | 200 | meter (number)
10 | 2001119870 | SCREW HEX SCK ALN BLT GR 12.9 80MM M8 Mat: HIGH TENSILE STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: IS 1367 PART-III GRADE 12.9 Type, thread: METRIC COARSE Length, thread mm 80MM Size: M8 | each | 200 | 200 | 200 | 200 | km (number)
12 | 2001119872 | SCREW HEX SCK ALN BLT GR 12.9 25MM M8 Mat: HIGH TENSILE STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: IS 1367 PART-III GRADE 12.9 Type, thread: METRIC COARSE Length, thread mm 25 Size: M8 | each | 200 | 200 | 200 | 200 | each
13 | 2000261967 | STDBLT+N N10276 UNC 0.625" 3.750" Mat spec, stud bolt(s): ASTM B574 UNS N10276 Mat spec, nut(s): ASTM B574 UNS N10276 Design spec, stud bolt: ASME B1.1 Design spec, nut: ASME B18.2.2 Thread class symbol, stud bolt 2A Thread class symbol, nut: 2B Type, thread: UNC Number, nuts per stud bolt: 2 Type, nut: HEAVY HEXAGONAL Add reqrmts: 2 PLAIN WASHERS Size: 0.625 INCH Length: 3.750 INCH MOC: HAST ALLOY-C | each | 88 | 88 | 88 | 88 | Piece
14 | 2000160132 | Parts for columns BOLT W/NUT;SIZE:M12X50;MOC:SS | each | 160 | 0 | 0 | 0 | Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM
2 | QAP/ITP/QCP | ITEMS: STUDS/BOLTS & NUTS REV.'0' DATE:10.04.2009 ASTM A 193, ASTM A 194 | na | APPROVED BY RIL
3 | Drawing(s)
4 | Procedure(s)
5 | Datasheet(s)
6 | Others (Specify)

## Stages Witnessed
Stages Witnessed
QAP Sr No: 4 Sample selection carried out for Mechanical Test.
QAP Sr No: 6 Visual check on 10% randomly selected samples from each item- No injurious defects was Found at time of Inspection.
QAP Sr No: 6 Threads checked with GO & NOGO gauge on 10% quantity from all item – Found satisfactory
QAP Sr No: 6 Dimension check on 10% randomly selected samples from each item-Found Within tolerance
QAP Sr No:7 PMI check on 10% randomly selected samples from each item as per approved QAP – Found to meet specification requirements
QAP Sr No:7 Hardness check on 10% randomly selected samples from each item as per approved QAP – Found to meet specification requirements
QAP Sr No: 6 Marking verified on 10% randomly fasteners from total offered quantity -Found to meet specification requirement

## Document reviewed
Document reviewed
QAP Sr NO:1 & 5 MTC & Lab Check Test Certificate of Raw Material For Mechanical test ( Tensile Test / Hardness Test / Proof Load Test) As Applicable & Chemical Analysis reviewed -Found in Order
QAP Sr NO:8 Final MTC NO: HI/985/986/987/988/989/990/2021-22 of Fasteners Reviewed-Found to meet specification Requirements

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Vernier Caliper | 0-300 mm | 180811100 | 01.12.2021 | NCQC¬M/021220/60 Dt.: 02.12.2020 | Yes |  | Yes
2 | PMI M/C |  | 97610 | 2022-08-06 | 1449-2021 |  | Yes | No
3 | HARDNESS TESTER | 250 kgf | 13/10/026 | 27.08.2022 | KTS/N/101/4-4/21-22 | Yes
4 | UNIVERSAL TESTINC MACHINE | 1000KN | UTE-100 | 27.08.2022 | KTS/N/101/2-4/21-22 | Yes
5 | Digital vernier caliper | 0-200mm | 500-199-30 | 04.07.2022 | NCQC-M/050721/28 | Yes
6 | MEASURING SCALE | 0 TO 1000MM | SC/01 | 04.07.2022 | NCQC-M/050721/24 | Yes

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: