## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number | 8118021368
Notification Number | Email Date 08.12.2021
Project Name & Location | Diesel Hydro Treating Unit (DHDT) & Hydrogen Generation Unit (HGU)M/s, HPCL Rajasthan Refinery Limited (HRRL), Barmer
Client Name | TOYO ENGINEERING INDIA PRIVATE LIMITED
End User Name | HPCL Rajasthan Refinery Limited ( HRRL )
DEC / PMC / EPC Name | EIL
DEC / PMC / EPC Number | B224
Vendor Name | Bombay Chemical Equipments
PO Number (Client PO on Vendor) | P/6403/38571/AXHG018C Dated 18/10/2021
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Wada
Inspection Date(s) | 09.12.2021

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | I109SP24011.50 | Y Type strainers', 1.5" x 800# SCH XS Ends SW (IBR), Commodity code : 109SP2401 | Piece | 1 | 1 | 1 | 1 | number
2 | I115SP75051.50 | Y Type strainers, 1.5" x 800# SCH XS Ends SW (IBR), Commodity code 115SP7505 | Piece | 1 | 1 | 1 | 1 | meter
3 | I109SP80043 | T type strainers, 3" x 150# SCH STD Ends BW, Commodity code: 109SP8004 | Piece | 1 | 1 | 1 | 1 | km
4 | I109SP85011.50 | Y type strainers, 1.5" x 800# SCH XS Ends SW, (IBR), Commodity code: 109SP8501 | Piece | 1 | 1 | 1 | 1 | meter (number)
5 | I109SP85021.50 | Y type strainers, 1.5"x 800# SCH XS Ends SW (IBR), commodity code: 109SP8502 | Piece | 1 | 1 | 1 | 1 | km (number)
6 | I109SP85031.50 | Y type strainers, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8503 | Piece | 1 | 1 | 1 | 1 | each
7 | I109SP85041.50 | Y type strainers, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8504 | Piece | 1 | 1 | 1 | 1 | Piece
8 | I109SP85051.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8505 | Piece | 1 | 1 | 1 | 1 | Test sample
9 | I109SP85061.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8506 | Piece | 1 | 1 | 1 | 1 | AU - All Unit
10 | I109SP85071.50 | Y type strainer, 1.5" x 800# SCH XS EndsSW (IBR), commodity code: 109SP8507 | Piece | 1 | 1 | 1 | 1 | lot
11 | I109SP85081.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8508 | Piece | 1 | 1 | 1 | 1 | Set
12 | I109SP85091.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8509 | Piece | 1 | 1 | 1 | 1 | Running Meter
13 | I109SP85101.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8510 | Piece | 1 | 1 | 1 | 1 | kg
14 | I109SP85111.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8511 | Piece | 1 | 1 | 1 | 1 | metric ton (tonne)
15 | I109SP85121.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8512 | Piece | 1 | 1 | 1 | 1 | ton
16 | I109SP85131.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8513 | Piece | 1 | 1 | 1 | 1 | cubic millimetre
17 | I109SP85141.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8514 | Piece | 1 | 1 | 1 | 1 | cubic centimeter
18 | I109SP85151.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP8515 | Piece | 1 | 1 | 1 | 1 | cubic meter
19 | I115SP33091.5 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 115SP3309 | Piece | 1 | 1 | 1 | 1 | cubic inch
20 | I115SP36111.5 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 115SP3311 | Piece | 1 | 1 | 1 | 1 | cubic foot
21 | I115SP60121.5 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 115SP6012 | Piece | 1 | 1 | 1 | 1 | mm
22 | I115SP60161.50 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 115SP6016 | Piece | 1 | 1 | 1 | 1 | cm
23 | I115SP75011.5 | Y type strainers, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP7501 | Piece | 1 | 1 | 1 | 1 | in
24 | I115SP75021.5 | Y type strainer, 1.5" x 800# SCH XS Ends SW (IBR), commodity code: 109SP7502 | Piece | 1 | 1 | 1 | 1 | foot
25 | I109SP80033 | T type strainers, 3" x 150# SCH STD Ends BW, Commodity code: 109SP8003 | Piece | 1 | 1 | 1 | 1 | mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | HBDH-PD-000-PIP-MRP-AXHG018 | NA | Client Document
2 | QAP/ITP/QCP | HBDH-VD-000-PIP-VPI-AXFG001 R02 | BCE-QC-ITP-1779 R02 | Approved by M/s.TEIPL in code A and M/s.TUV India in code AP.
3 | Drawing(s) | HBDH-VD-000-PIP-DWG-AXHG018C-0001 R01, HBDH-VD-000-PIP-DWG-AXHG018C-0002 R02, & HBDH-VD-000-PIP-DWG-AXHG018C-0003 R02 | BCE-STR-1846-01 R01, BCE-STR-1846-02 R02 & BCE-STR-1846-03 R02 | Approved by M/s.TEIPL in code A.
4 | Procedure(s) | HBDH-VD-000-PIP-VPI-AXFG001 R00 | BCE-QC-SPPP-1846 R00, BCE-QC-WPS-PQR-1779 R03 | Approved by M/s.TEIPL in code A.
5 | Datasheet(s) | HBDH-ED-109-PRS-DAT-SPP-0001 | NA | Clien Document
6 | Others (Specify) | NA | NA | NA

## Stages Witnessed
Stages Witnessed
QAP Sr.No V: Visual check of 100% of offered strainers from outside and inside (accessible area) for surface condition and workmanship for all offered strainers – Found free from injurious surface defects at the time of inspection.
QAP Sr.No V: Final Dimension inspection of strainers & completeness of all fabrication activity as per approved drawing witnessed for 10 % randomly selected strainers from offered strainers Found to meet requirements of approved drawing
QAP Sr.No VI: PMI check of 100% quantity of filters (including spare filters) & 10% studs randomly are witnessed and alloying elements found to meet respective material specification requirement.
QAP Sr No IV: Witnessed Hydrostatic Test of 10% Strainers from offered lot as per approved drawing for holding period of 15 minutes, No leakage & no pressure drop observed during holding period- found acceptable. (Strainers Hydrostatic test carried out with filter element inside)
QAP Sr No III: Witnessed DP Test of 10% Strainers from offered lot for Bevel End & at accessible areas of all welds as per ASEM Sec VIII Div1, Appendix 8- found satisfactory.
QAP Sr No VII: Witnessed Fitment of filter element before final assembly of 10% T- Type Strainers from offered lot- found satisfactory.
QAP Sr No VI & VIII: Witnessed Final Paint Visual & DFT of Strainer as per approved painting procedure- found satisfactory.
QAP Sr No VIII: Witnessed Packing of 100% Spare Strainers of T-Type Strainer as per approved ITP - found in order.
QAP Sr No II: Reviewed Radiography Films of T-Type Strainers Butt Welds as per ASME Sec VIII Div 1, UW-51- found satisfactory.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Sr No I.A: Reviewed Raw Material TC (Flanges, Plug, fasteners, gaskets, Tee, Body & Cover) as per specification- found satisfactory.
QAP Sr No I.B: Reviewed Lab Test records of Internals (Mesh & Mesh Frame) & Plates as per specification- found in order.
QAP Note No 16: Reviewed WPS/PQR/WPQ as per ASME Sec IX- found in order.
QAP VII & IX: Reviewed Work Test certificate (1846-1 Dated 29.11.2021, 1846-2 to 1846-04 Dated 29.11.2021) and Copy of IBR FORM III-C (BCE/BVIL/2020-21/IIIC-284 Dated 04.11.2020) as per specification- found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern
None

## Pending Activities
Pending Activities from this visit
None

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: