## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 010101145721/20
SAP number | 8118997801
Notification Number | DEM/-KPTL/BALL/SVITA/MECON/2021-22/04 Email Dated - 24.01.2022
Project Name & Location | North East Gas Grid (NEGG) Project - Part A
Client Name | Kalpataru Power Transmission Limited (31127)
End User Name | Indradhanush Gas Grid Limited (36014)
DEC / PMC / EPC Name | Mecon Ltd Delhi
DEC / PMC / EPC Number | Not Applicable
Vendor Name | DEMBLA VALVES LIMITED (38243)
PO Number (Client PO on Vendor) | 2300122188 Dated - 10.06.2021
Sub Vendor | Not Applicable
PO Number (Vendor PO on Sub Vendor) | Not Applicable
Inspection Location | A/8 Arham Logicpark Village - Valishind, Mumbai Nashik National Highway ( NH3 ) Taluka : Bhiwandi, District : Thane, State : Maharashtra - 421302
Inspection Date(s) | 27.01.2022, 28.01.2022, 29.01.2022 & 31.01.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | F651-141 | Hand Wheel Operated Diaphragm Valve, Weir Type Size: DN 15 [1/2"] X 150# , FE, RF MOC: ASTM A351 Gr CF8 (SS) Tag No.: DWF0132W Valve Sr no: E224673‐1 TO E224673‐7 Witnessed Valve Sr no:E224673‐5 | number | 7 | 7 | 7 | 7 | number
2 | F651-141 | Hand Wheel Operated Diaphragm Valve,Weir Type Size: DN 20 [3/4"] X 150# , FE, RF MOC: ASTM A351 Gr CF8 (SS) Tag No.: DWF0132W Valve Sr no: E224673‐8 Witnessed Valve Sr no:E224673‐8 | number | 3 | 1 | 1 | 1 | meter
4 | F651-141 | Hand Wheel Operated Diaphragm Valve, Weir Type Size: DN 40 [1 1/2"] X 150# , FE, RF MOC: ASTM A351 Gr CF8 (SS) Tag No.: DWF0132W Valve Sr no: E224673‐15 TO E224673‐18 Witnessed Valve Sr no:E224673‐16 | number | 4 | 4 | 4 | 4 | km
5 | F651-141 | Hand Wheel Operated Diaphragm Valve, Weir Type Size: DN 50 [2"] X 150# , FE, RF MOC: ASTM A351 Gr CF8 (SS) Tag No.: DWF0132W Valve Sr no: E224673‐19 TO E224673‐24 Witnessed Valve Sr no:E224673‐20 | number | 6 | 6 | 6 | 6 | meter (number)
6 | F651-141 | Hand Wheel Operated Needle Valve, Needle Type Size: DN 15 [1/2"] X 800# , SW MOC: ASTM A105 (CS) Tag No.: NGS0856 Valve Sr no:E224673‐25 Witnessed Valve Sr no:E224673‐25 | number | 1 | 1 | 1 | 1 | km (number)
7 | F651-141 | Hand Wheel Operated Needle Valve, Needle Type Size: DN 20 [3/4"] X 800# , SW MOC: ASTM A182 Gr F304L (SS) Tag No.: NGS0871A Valve Sr no:E224673‐26 TO E224673‐31 Witnessed Valve Sr no:E224673‐30 | number | 6 | 6 | 6 | 6 | each
9 | F651-141 | Self Operated Dual Plate (Retainer Less) Check Valve Size: DN 250 [10"] X 150# , Wafer MOC: ASTM A216 Gr WCB (CS) Tag No.: WCW0131 Valve Sr no:E224673‐34 TO E224673‐35 Witnessed Valve Sr no:E224673‐34 | number | 2 | 2 | 2 | 2 | Piece
10 | F651-141 | Self Operated Ball Type Check Valve Size: DN 50 [2"] X 150# , FE, RF MOC: ASTM A182 GR.F304 (SS) Tag No.: BCF0131W Valve Sr no: E224673‐36 Witnessed Valve Sr no:E224673‐36 | number | 1 | 1 | 1 | 1 | Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | WB-F61-F651-151 Rev.0 | DVL-ITP-00 Rev.B (DVL/QAD/F004 - R00) | Approved With Minor Comments by JFE in Code-B
3 | Drawing(s) | WB-C45-F651-151 Rev.0 | DVL-GAD-00 Rev.C Page 1 To 8 (GAD-E-04673-DV-01-R1, PO LI 1,2,4,5 GAD-E-04673-NV-02-R1, PO LI 6 GAD-E-04673-NV-03-R1, PO LI 7 GAD-E-04673-DPCV-05-R1, PO LI 9 GAD-E-04673-BCV-04-R1, PO LI 10) | Approved By JFE in Code-A
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
QAP Stage no. E1: Shell hydrostatic test witnessed as per approved GAD & ITP on 10% randomly selected Qty. from offered PO Line item - No leakages and No pressure drops observed during holding time.
QAP Stage no. E2: Seat hydrostatic test witnessed as per approved GAD & ITP on 10% randomly selected Qty. from offered PO Line item - No leakages and No pressure drops observed during holding time.Except for Check valve (10" x 150#, E224673‐34) observed seat leakage 15ml/minute-Found to meet API 598 requirement.
QAP Stage no. E3: Seat Pneumatic test (Except Check Valve) witnessed as per approved GAD & ITP on 10% randomly selected Qty. from offered PO Line item - No leakages and No pressure drops observed during holding time.
QAP Stage no. E4: Before painting, Visual checked (Outside & inside feasible area) cndition, on 10% randomly selected Qty. from offered PO Line item-Found free of Rust, pits, cracks & obvious defects at the time of inspection.
QAP Stage no. E4: Dimesnion (F-F, flange OD, Thk, PCD, No of holes, size of holes etc) checked as per approved drawing by vendor provided calibrated Vernier caliper on 10% randomly selected Qty. from offered PO Line item-Found to meet approved drawing requirement.
QAP Stage no. E5: Operation (open & close) checked manually on 10% randomly selected Qty. from offered PO Line item-Found smooth operation at the time of inspection
Marking checked on offered valve (Engraved/Hard Punch Mfg. Logo [DEMBLA], Size, Class, Grade, Body & Bonnet Heat No, valve Sr no) -Found to meet QAP requirement
All measuring Instruments/ Equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Stage No. A1: Raw material test certificates for Body, Bonnet, Cover declared by supplier on offered qty.–Found to meet ITP & material specification requirement
QAP Stage No. A2: Raw material test certificates for Ball, Needle, disc & Stem declared by supplier on offered qty.–Found to meet ITP & material specification requirement
QAP Stage No. A3: Raw material test certificates for Body-bonnet fasteners declared by supplier on offered qty.–Found to meet ITP & material specification requirement
Manufacturer test certificates as per EN10204:3.1 reviewed-Found to meet ITP & drawing requirement.
Painting report submitted by vendor-Found in order

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
PO Sr. No. 10 Valves provisionally hard stamped as " " for identification near manufacturer marking subjected to points mentioned in area of concrn column.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable subjected to manufacturer action on points mentioned in area of concern column.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: