## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 050101088121/109/1
SAP number | 8119036374
Notification Number | As Per Email Dtd.07.02.2022
Project Name & Location | HPCL ARC Job
Client Name | Hindustan Petroleum Corporation Ltd.
End User Name | Hindustan Petroleum Corporation Ltd.
DEC / PMC / EPC Name | Not Applicable
DEC / PMC / EPC Number | Not Applicable
Vendor Name | S Prasad Construction Co.
PO Number (Client PO on Vendor) | 21000709-OS-48002/RA Dtd.24/11/2021
Sub Vendor | Vinfab Engineering India Pvt. Ltd.
PO Number (Vendor PO on Sub Vendor) | HPCL Gate Pass No. 48000-R-194181 Dtd.08/12/2021
Inspection Location | Gut No. 224, Bhiwandi Wada Highway, Khupri Village, Wada
Inspection Date(s) | 2022-02-07

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | S1006479 | Hot Dip Galvanized 6" Pipe With Flange Welded Both Sides | number | 3 | 3 | 3 | 3 | number
1 | S1006479 | Hot Dip Galvanized 8" Pipe With Flange Welded Both Sides | number | 17 | 17 | 17 | 17 | meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | INSP/QAP-113 Rev.1 Dtd.19/03/2019 | Not Applicable | Approved By Client
3 | Drawing(s) | Not Applicable | Not Applicable | Not Applicable
4 | Procedure(s) | Not Applicable | Procedure For Hot Dip Galvanizing | Reviewed By TUVIPL
5 | Datasheet(s) | IS:4736, IS:2629, IS:4759 & IS:2633 | Not Applicable | Not Applicable
6 | Others (Specify) | HPCL Gate Pass No. 48000-R-194181 Dtd.08/12/2021 | Not Applicable | Issued By HPCL

## Stages Witnessed
Stages Witnessed
As per QAP clause no. 1.2, Visual inspection for 10% qty. of randomly selected pipe spools from offered lot was witnessed to check outside surface area & inside accessible visible area - Found in HDG condition and free from injurious surface defects, hence acceptable.
As per QAP clause no. 1.2, Zinc coating thickness (DFT) of 10% qty. of randomly selected pipe spools from offered lot was checked with elcometer and coating thickness found to meet P.O. & specification requirements (i.e. 100 microns min.), hence acceptable.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
As per QAP clause no.1.1, Procedure for Hot dip galvanizing as declared & submitted by vendor for offered lot was reviewed and found to meet specification requirements, hence acceptable.
As per QAP clause no.1.3, Inspection report for galvanizing test such as adhesion test, preece test, mass of zinc coating & DFT check with elcometer carried out by vendor for offered lot of pipe spools was reviewed and found to meet specification requirements, hence acceptable.
As per QAP clause no. 2.0, All Inspection documents for offered lot of pipe spools was reviewed / verified and found to meet P.O. & QAP requirements, hence acceptable.
Calibration certificates for testing equipments used during inspection was reviewed and found in order, hence acceptable.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Coating Thickness Gauge | 0-999 Microns | CTG-01 | 2022-03-05 | IK-050321-02/01 Dtd.09-03-2021 | Yes |  | Yes
No

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Nil
Identification of Inspected Item(s):
Not Applicable
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable
IRN can be issued for PO Item numbers:
No
Expenses:
Remarks: