## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number | 8120307920
Notification Number | Email Dated 06.07.2023
Project Name & Location | 850 TPD, Jhagadia
Client Name | DCM Shriram Alkali & Chemicals
End User Name | DCM Shriram Alkali & Chemicals
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name | SSJ Engineers & Exports Pvt Ltd
PO Number (Client PO on Vendor) | SAC/B05/4250010531 Dated 03.08.2022
Sub Vendor | DOSHI FABRICATORS PVT LTD
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Boisar
Inspection Date(s) | 08.07.2023

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
00010 | 266808 | TANK MOLTEN_SALT 17.6M3 Tag No. 02-T-6101 & 03-T-6101 | number | 2 | 2 | 2 | 2 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | NA | NA | NA
2 | QAP/ITP/QCP | NA | SSJ/2022/ 391 REV-1 Dt. 18.03.22 | APPROVED BY CLIENT
3 | Drawing(s) | NA | SSJ/2022/ 391 A & B REV-1 | Approved by Client
4 | Procedure(s) | NA | NA | NA
5 | Datasheet(s) | NA | NA | NA
6 | Others (Specify) | NA | NA | NA

## Stages Witnessed
Stages Witnessed
QAP Line No 1.A,B,C: Material identification witnessed for pressure parts as per approved QAP & Drawing- found satisfactory.
QAP Line No 4.ii: Reviewed Radiography Films of LS & CS Joints as per ASME Sec VIII Div1, UW 52- found satisfactory.
QAP Line No 7: Visual Inspection carried out of Equipments for Completenss & from outside & acceissible Inside area for workmanship, condition & finish- found satisfactory.
QAP Line No 6: Witnessed Dimensional Inspection of Equipments as per approved drawing - found satisfcatory.
QAP Line No 8: Witnessed hydrostatic test of Tanks at pressure of 0.8 kg/cm2(g) (Actual 1 kg/cm2(g)) for holding period of 60 minutes, No Leakge observed during holding period - found satisfactory.
QAP Line no 9: Reviewed Final Paint DFT Check report as per specification & client email dated 17.07.2023 - found in order.
CRS Line no 13: Random Witnessed PMI Check of SS Parts of Tank as per approved drawing & specification- found in order.
CRS Line No 16: Visual inspection carried of Tanks from outside & inside after Pickiling Passivation as per A 380 and Witnessed CuSO4 Test at random locations after Pickling Passivation - found satisfatory.
Name Plate verified as per approved drawing - found in order.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Line No 3.iv: Reviewed WPS/PQR/WPQ as per ASME Sec IX- found in order.
QAP Line No 3.iv: Reviewed PQR as per ASME Sec IX- found in order.
Reviewed Welding Consumable Batch Test Certificate as per ASME Sec II Part C- found in order.
QAP Line No 3.i, ii & iii: Reviewed Long Seam Set-up, Circ Seam Set-up & Nozzle reports of as per approved drawing - found in order.
QAP Line No 4.i: Reviewed LS, CS & Nozzle Backchip DP Reports as per ASME Sec VIII Div1, Appendix 8- found in order.
QAP Line No 4.iii: Reviewed PWHT Chart of Equipments as per specification - found in order.
Reviewed Primer Batch Test Certificate as per specification - found in order.
QAP Line No 5: Reviewed Pneumatic Test reports of RF Pads as per approved QAP & drawing - found in order.
QAP Line No 1.A, B, C, D: Reviewed Raw Material TC (Plate, Pipe, Flanges) & Copy of IBR form IIIB - found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Coating Thickness Gauge | 0-1300 microns | CTG-01 | 09.04.2024 | 2023/RES/C236898 Dated 12.04.2023 | Yes |  | Yes
No

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
NA
Identification of Inspected Item(s):
Name Plate hrad Single hard stamp as " " for Identification.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable.
IRN can be issued for PO Item numbers:
NO.
Expenses:
Remarks: