## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number
Project Name & Location | 8119397952
Client Name | Reliance industries Ltd
End User Name | Reliance industries Ltd
DEC / PMC / EPC Name | L&T Hydrocarbon engineering Pvt Ltd.
DEC / PMC / EPC Number | E1204
Vendor Name | Flowserve India controls Pvt Ltd
PO Number (Client PO on Vendor) | 336-240391750
Sub Vendor | Deccan Hitech engineering Pvt Ltd.
PO Number (Vendor PO on Sub Vendor) | 199818
Inspection Location | Deccan Hitech Engineering Pvt. Ltd., Poonnamalli, Chennai
Inspection Date(s) | 07.07,2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 4500672306 | 2H164317 -PLAN 52 For MX SORBEX FEED PUMP , Tag No: G-5106 A (2 seals system Drive End,Non Drive End) | number | 1 | 1 | 1 | 1 | number
2 | 4500672306 | 2H164317 -PLAN 52 For MX SORBEX FEED PUMP , Tag No: G-5106 B | number | 1 | 1 | 1 | 1 | meter
3 | 4500672310 | 2H164317 -PLAN 52 For MX SORBEX FEED PUMP , Tag No: G-5106 -CAPSPARE. | lot | 1 | 1 | 1 | 1 | km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | MT-P20P01-D1PAX-MPP001-MEC-P-00 |  | Not Applicablr
2 | QAP/ITP/QCP | MT-P20P01-D1PAX-MPP006-MEC-P-00-A-AX501-A05-0004 -02 | BM21105004-001-6722-02 Rev B | Approved by RIL in code 1
3 | Drawing(s) | MT-P20P01-D1PAX-MPP006-MEC-P-00-A-AX501-F05-0002 -03 | 2H-164436 Rev 3 | Approved by RIL in code 1
4 | Procedure(s) | NIL
5 | Datasheet(s) | MT-P20P01-D1PAX-MPP006-MEC-P-00-A-AX501-D03-0005 -03 | BM21105004-001-6706-01 | Approved by RIL in code 1
6 | Others (Specify)

## Stages Witnessed
Stages Witnessed
Visual inspection was carried out on the offered API Plan 52 system assembly. BOM verifications, Nozzle Orientations, Completeness of the system was carried out as per drawing and found satisfactory. -Found acceptable and reports attested for records.
Hydro Test of the complete system without instruments witnessed for 30 minutes @ 126 Kg/Sq.cm -Found No pressure drop or leakage was observed and Report attested for records.- Found acceptable and reports attested for records.
Hydro Test of the Coil Shell was witnessed for 30 minutes @ 15 Kg/Sq.cm and No pressure drop or leakage was observed and found satisfactory. Report attested for records.
Witnessed Dimensional check for offered system with respect to approved drawing.– Found within acceptable limits and reportd attested for records.
PMI of examination of SS parts,weldment including fasteners were checked randomly by 10% Qty and values found accepatble with respect to material standard. Reports attedted for records.
Verified instrumets identificationmark ,model number ,mfr name,sl no,area clasification ,and assembly on system with cannopy arrangemnet-Found inorder
Name plate verification was carried out in loose condition and found in order with respect to drawing.

## Document reviewed
Document reviewed
Pressure part Raw material test certificates of SS parts were reviewed for Pipes, Tubes, Dish Ends, Plates, Pipe Fittings, Flanges, Reducers and found in order with respect to QAP & Project specifications. Attested for records.
Manufacturer test certificates of valves, Handpumps were reviewed and found in order with respect to QAP & Project specifications. Attested for records.
Non Pressure part Raw material test certificates of CS Parts were reviewed for Pipes, Plates and found in order with respect to QAP & Project specifications. Attested for records.
Welding consumables batch certifiacte was reviewed and found in order with respect to QAP & Project specifications. Attested for records.
Applicable WPS / PQR / WPQ documents were verified and found in order. Attested for records.
Fitup report was reviewed and found in order. Attested for records.
DP report of butt joint weld and fillet joint weld was reviewed and found in order. Attested for records.
Cooler assembly documents were reviewed and Cooler butt weldments 10% Radiography films reviewed -Found in order with respect to QAP & Project specifications. Attested for records.
CS parts Painting report reviewed as per QAP requirement -Found acceptable and reports attestedf for records,
Reviewed cooler open coil hydro test report -Found acceptable and reports ttested for records.
Pickling & passivation report was and found in order with respect to QAP & Project specifications. Attested for records.
PMI report reviewed 100% of components with respect to QAP & Project specifications. Attested for records.
DM water test certificate was reviewed and found in order with respect to QAP & Project specifications. Attested for records.
Calibration status of the equipments / instruments used for inspection was verified and found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Pressure gauge | 0-280 kg/cm2 | PG-40 | 31.10.2022 | SC-1548-02/21 | Yes |  | Yes
2 | Pressure gauge | 0-280 kg/cm2 | PG-39 | 31.10.2022 | SC-1548-01/21 | Yes |  | No
3 | Vernier Caliper | 0 to 300mm
4 | Pressure gauge | 0-42 kg/cm2 | PG-21 | 17.01.2023 | MKBS/22/01035-002 | yes
5 | measuring tape | 0-5 Mtr | DHEPL/MT-007 | 28.12.2022 | C22012100029537F | Yes
6 | PMI Machine | XL 2 800 | 98462 | 07.11.2022 | GAS/ML/42 |  | Yes

## Areas of concerns
Areas Of Concern
None

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
NIL
Identification of Inspected Item(s):
Each equipment having TUV hard stamp for identification
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptanle
IRN can be issued for PO Item numbers:
Not Applicable
Expenses:
Remarks: