## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 050106154921/2
SAP number | 8119254777/100
Notification Number | Mail Dt 03.12.2021
Project Name & Location | NA
Client Name | MANALI PETROCHEMICAL LIMITED(5780)
End User Name | MANALI PETROCHEMICAL LIMITED(5780)
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | GULF ENGINEERS AND CONSTRUCTORSPVT LTD(187)
PO Number (Client PO on Vendor) | 6200003289 Dated 19.11,2020
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Ernavoor
Inspection Date(s)
EPC Contractor | None

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 2002275432 | EO STRIPPER REBOILER, Tag No : 3-E-311 | each | 1 | 1 | Refer Area of Concern |  | number
2 | 2002014378 | HR REBOILER, Tag No : EA-3206 | each | 1 | 1 | Refer Area of Concern |  | meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | NIL | PE/ITP/1806-1 REV.2 & PE/ITP/1806-2 REV.2 | Approved by RIL Via Mail Dt: 10.05.2023 & 13.06.2023
3 | Drawing(s) | NIL | PE/2110/HE/E311/22 Rev.01 & PE/2111/HE/EA-3206/22 Rev.0 | Approved by RIL Via Mail Dt: 16.06..2023 & 02.06.2023
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
QAP Sl. No.: 6.1 - Witnessed Material Identification carried out on offered C.S Plates for Tag No : EA-3206 correlated with manufacturer test certificate verified Original marking, Manufacturer name, Heat number, Plate Number, Material grade, Size and Thickness – Found satisfactory.
QAP Sl.No.: 6.2 - Witnessed Material Identification was carried out on offered Pipes for Tag No : EA-3206 and correlated with manufacturer test certificate verified Original marking, Manufacturer name/Logo, Heat number, Material grade, Size and Thickness – Found satisfactory.
QAP Sl.No.: 6.3 - Witnessed Material Identification was carried out on offered CS (STD Forgings), for Tag No : EA-3206, correlated with manufacturer test certificate verified Original marking, Manufacturer name/Logo, Heat number, Material grade, Size and Thickness – Found satisfactory.
QAP Sl. No.: 6.1 - Each Part identification and PTC Test coupon identified with TUV hard stamp - Found satisfactory.
QAP Sl. No.: 6.2 & 6.3 - Each Part identification identified with TUV hard stamp - Found satisfactory.
QAP Sl. No.: 6.4 - Witnessed Material Identification was carried out on offered Non Std Forging, Material : SA 266 Gr.2 for Tag No : EA-3206 correlated with manufacturer test certificate verified Original marking, Manufacturer name, Heat number, Material grade, Size and Thickness – Found satisfactory.and each forging TUV hard stamped for identification.
QAP Sl. No.: 6.4 - Each Part identification for Non Std Forging and identified with TUV hard stamp - Found satisfactory.
ITP Sl. No.: 6.5 - Witnessed Material Identification was carried out on offered C.S Seamless tubes, Material : SA 179 for Tag No : EA-3206 and correlated with manufacturer test certificate verified Original marking, Manufacturer name, Heat number, Material grade, Size and Thickness – Found satisfactory.
ITP Sl.No.: 7.3 - Witnessed Mechanical testing of test coupon in Normalized Condition for Top and Bottom Channel dish for Tag No : EA-3206 - Found satisfactory with respect to Material standard and approved drawing.
ITP Sl.No.: 7.4 - Visual and dimensional inspection was carried out on offered Top and Bottom Channel dish after PFHT, verified (Total height, Inner diameter, ICF, Thickness, Profile Check & Template (Internal & external)) for Tag No : EA-3206 – Found within acceptable tolerance as per approved drawing.
ITP Sl.No.: 7.4 - Witnessed LPT was carried out on both inside/outside surface of Knuckle radius, Straight Face and Bevel edges of Top and Bottom Channel dish after PFHT for Tag No : EA-3206 – No surface defects were observed.
ITP Sl.No.: 7.4 - Witnessed Hardness test was carried out on offered Top and Bottom Channel dish head after PFHT for Tag No : EA-3206 - Value are within 200 BHN with respect to Hardness Procedure.
ITP Sl.No : 9.9 – Witnessed Internal Visual and dimensional inspection was carried out on offered Shell ,channel assembly for Tag No : EA-3206 – Found within acceptable tolerance as per approved drawing.
ITP Sl.No : 10.1 - Witnessed Visual and Dimensional inspection was carried out for offered Top and Bottom Tubesheet after machining and drilling for Tag No : EA-3206 – Found within tolerance with respect to approved drawing.
ITP SL No.: 10.7 Witnessed Tube to tube sheet joint pneumatic test with soap solution after final welding For Tag No : EA-3206 -Found no leak ,pressure drop observed and reports attested for records.
ITP SL No. 10.8 Witnessed random selected tubes on both side Tube to tube sheet joint expension check ( Percentage of expansion,expansion length ) as per approved drawing and procedure -Found within acceptable limits,.
ITP SL.No: 10.10 - Witnessed Helium leak test at,10 % concentration , Pressure at 1 Kg/cm2 (g) was carried out on Tube to Tube sheet joint after final Welding ,after Expansion of Top and Bottom Stationary Tubesheet for Tag No : EA-3206 - By snifing method - Found leak rate within acceptable limits.
ITP Sl.No : 10.11 – Witnessed Visual and dimensional inspection was carried out on offered heat exchanger assembled condition( orientation ,nozle projection ,external attachment sizes and weld size gasket seating faces for Tag No : EA-3206 – Found within acceptable tolerance as per approved drawing.
ITP SL No 10.14 Witnessed Spares+ loose tems and Name plate verification as per approved drawing -Found acceptable
ITP SL.No: 11.1 - Witnessed Shell side hydro test including tube to tube sheet joint as per approved drawing and procedure at, Pressure at 55.11 Kg/cm2 (g) 1 hour for Tag No : EA-3206 - Found no leak ,pressure drop observed
ITP SL.No: 11.2 - Witnessed Tubeside hydro test as per approved drawing and procedure at, Pressure at 16.85( 17.0) Kg/cm2 (g) 1 hour for Tag No : EA-3206 - Found no leak ,pressure drop observed
ITP SL No: 11.3 Witnessed draining and drying for Tag No: EA-3206 as per approved ITP and measured relative humidity in both shell side and tube side -Found within acceptable limits
ITP SL No. 12.1 surface preparation visual check carriedout for offered Heat exchanger Tag No. EA-3206-Found (near white ) surface acceptable
ITP SL No 12.1 Surface preparation dust level ,salt contamination , Profile checked as per approved drawing and procedure -Found acceptable and report attested for records.
ITP SL No.: 12.1 Witnessed painting Visual,DFT and adhesion test ( Tape test and Pull of test) as per approved QAP ,drawing requirement and verified the coating systems -Found acceptable and reports attested for records.
ITP SL No 13.1 verified stamping on equipment ( Tube sheet and channel flange) and name plate details as per approved drawing and TUV hard stamped on Tube sheet OD and Channel flange OD near Marking.
ITP SL No13.3 witnessed packing (verified equipment marking ,caution marking ,N2 Purging,temporaray flanges and 100% boltings for nozzle with out permanent dummy ,rust preventive applied on fasteners and n2 Refilling arrangement )-Found inorder.
ITP SL No, 13.5 Final Documentation verified ( Completion of all inspection & test records and other documents) -Found inorder.

## Document reviewed
Document reviewed
QAP Sl. No.: 6.1 - Reviewed Photocopy of Manufacturer Test Certificate for offered C.S Plates, for Tag No : EA-3206 - Found meets to Material specification, drawing requirement -Found acceptable
QAP Sl.No.: 6.2 - Reviewed Photocopy of Manufacturer Test Certificate for offered CS Pipe, for Tag No : E311 - Found meets to Material specification, drawing requirement and TDC.-Found acceptable
QAP Sl.No.: 6.3 - Reviewed Photocopy of Manufacturer Test Certificate for offered CS (STD Forgings),, Material : SA 105 for Tag No : EA-3206 - Found meets to Material specification, drawing requirement and TDC.
QAP Sl.No.: 6.3 - Reviewed Magnetic Particle Test report And Ultrasonic test report for offered CS (STD Forgings) for EA-3206 - Found In order.
ITP SL No : 6.6 Reviewed Non pressure part Test certificates and material identification reports for Tag No. EA-3206 as per approved drawing -Found acceptable -Found acceptable and reports attested for records
ITP SL No. : 6.7 Reviewed Fasteners and Gasket test certificate as per material specification and drawing-Found acceptable and reports attested for records.
ITP SL NO. 6.8 Reviewed welding consumable batch certificates as per material specification -Found acceptable and reports attested for records.
ITP SL No: 7.1 Reviewed Dished end after forming Report ( visual,Dimensional,DP test report on Dish Knuckle portion inside and outside and template check ( Inside and outside)-Found acceptable and reports attested for records.
ITP SL No.: 7.2 Reviewed Normalising Heat treatment chart for Top and Bottom Channel dish head after forming for Tag No : EA-3206 – Found in order.
ITP SL No.: 8.1 & 8.3 Reviewed Fit up report for Long seam fit up of rolled nozzles ,flange to nozzles branch Nozzles to main nozle as per approved drawing -Founmd acceptable and reports attested for records.
ITP SL No.: 8.2& 8.4 Reviewed PT report for bevel edges, PT after root back chip and Final weld as per approved procedure -Found acceptable
ITP SL No :9.1 Reviewed long seam Fit up report for shell and channel assembly ( Alignement,PT on bevel edge and dimensions) as per approved drawing -Found acceptable
ITP SL No.9.2 Reviewed shell long seam weld PT report for after root back chip and Final weld as per approved procedure -Found acceptable
ITP SL No.9.2 Reviewed shell long seam Phased array Ultrasonic test report as per approved procedure -Found no relavant indication observed.
ITP SL No. : 9.3 Reviewed Fit up report for Nozzles to shall and channel shall assembly for Tag No. EA-3206 as per approved drawing -Found acceptable and reports attested for records
ITP SL No.: 9.4 Reviewed Shell , Channel to nozzle Root back cip & final weld PT report for Tag No.EA-3206 -Found acceptable and reports attested for records.
ITP SL No : 9.5 Reviewed Shell , Channel to External attchement welds PT& MT report for Tag No. EA-3206 -Found acceptable and reports attested for records
ITP SL No. : 9.6 Reviewed Temporary attchements removal area on Top and bottom channel shell and shell assembly PT reports for Tag No EA-3206 -Found acceptable and reports attested for records
ITP SL No.: 9.7 Reviewed Pull through gauge check report for Shell assembly for Tag No EA-3206 -Found acceptable and reports attested for records.
ITP SL No. : 9.8 Reviewed RF Pad Pneumatic leak test t 1.05 kg/cm2on Top and bottom channel and Top and bottom flange to barrel joint as per approved drawing for Tag No. EA-3206 -Found acceptable and report attested for records.
ITP Sl.No.: 10.2 - Reviewed Dimension report for baffles plate after drilling for Tag No : EA-3206 as per approved drawing – Found in order.
ITP SL No.:10.3 Reviewed report for Tube bundle skeleton assembly with tube sheet and baffle/supports as per approved drawing -Found within acceptable limts.
ITP SL No.: 10.4 Reviewed Fit up report for Tube sheet with shell assembly after bundle insrtion CS Joints as per approved drawing -Found acceptable
ITP SL No.: 10.5 Reviewed Tubesheet with shell CS joint PT report for Root back chip and Final weld as per approved procedure -Found no recordable indocation observed.
ITP Sl.No : 10.6 - Reviewed Root and Final weld DPT report for Tube to Tubesheet Joint of Top and Bottom Stationary Tubesheet for Tag No : EA-3206 – Found in order.
ITP SL No :10.9 Reviewed Final weld after expansion DPT report for Tube to Tubesheet Joint of Top and Bottom Stationary Tubesheet for Tag No : EA-3206 – Found in order
ITP SL No 10.12 Reviwed all inspection reports . Material heat chart and NDT Consolidation reports bfore hydro test-Found inorder
ITP SL No. 12.2 Reviewed nitrogen purging report ( N2 pressure,Oxygen level) as per approved procedure-Found acceptable .
ITP SL No.13.2 Reviewed As bulit drawings and verified ( dimensional changes ,material chages) -Found inorder and as built drawings attested for records.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Measuring Tape | 0 to 5 Mtrs | PE-II-MT-204 | 16.11.2023 | Tii230517-6-25 | Yes |  | Yes
2 | Veriner Caliper | 0 to 300mm | PE-II-VC-124 | 23.12.2023 | CC256423000004218F | Yes |  | No
3 | Pressure Gauge | 0 to 4.2 kg/cm2 | PE-I-PRG-09 | 18.01.2024 | Tii-230719-5-22 | Yes
4 | Pressure Gauge | 0 to 4.2 kg/cm2 | PE-I-PRG-10 | 18.01.2024 | Tii-230719-5-8 | Yes
5 | MSLD Machine | ASM 310 | HLD1701386 | 10.01.2024 | Cert Dt 09.01.2023 |  | yes
6 | SLC Cylinder | FV4810 | FC19000937 | 22.01.2024 | Cer Dt 23.01.2023 |  | yes
Type equation here.
"Type equation here."

## Areas of concerns
Areas Of Concern
Previous Open Points - Vendor Offered all Plate (32Thk) Trader endorsement was not available. M/s. PECPL to submit Trader endorsed MTC for TUV India Review.
Previous Open Points - For offered C.S Plates, Size : 18Thk, (H.T No - R13368, P.No - HT1569111N) And CS Pipe, Size: OD 88.9 X 11.13 THK (H.T No - M00693013). M/s. PECPL to Submit Check Test report for TUV India Review.
Previous Open Points - For offered C.S Plates, Size : 18Thk, (H.T No - R13368, P.No - HT1569111N) Manufacturer Name : ArcelorMittal Nippon Steel India Ltd was not in Approved Vendor List. M/s. PECPL to Give Justification.

## Pending Activities
Pending Activities from this visit
Vendor to Offer all Witness/Review Stage to TUV India as per ITP.

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: