## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 050106154921/2
SAP number | 8119254777/100
Notification Number | Mail Dt 03.12.2021
Project Name & Location | NA
Client Name | MANALI PETROCHEMICAL LIMITED(5780)
End User Name | MANALI PETROCHEMICAL LIMITED(5780)
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | GULF ENGINEERS AND CONSTRUCTORSPVT LTD(187)
PO Number (Client PO on Vendor) | 6200003289 Dated 19.11,2020
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Ernavoor
Inspection Date(s)
EPC Contractor | None

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
7 | 4500720856 | USG DEPROPANIZER FEED CHILLER, Tag No : ME-CRC301-S110006 | each | 1 | 1 | 1 | 1 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | MT-J21P19-D1JCR-MES002-TPD-Q-02 | NIL | RIL MRQ No
2 | QAP/ITP/QCP | J21P19-D1JCR-MES002-TPD-P-02-A-C301-A05-002 Rev.02 | PE/ITP/1793/02 Rev.02 | Approved by T.EN in code.03
3 | Drawing(s) | J21P19-D1JCR-MES002-TPD-P-02-A-C301-B02-005 Rev.02 | PE/2057/HE/ME-CRC301-S110006/22 Rev.02 | Approved by T.EN in code.03.
4 | Procedure(s) | LPT : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-001 Rev.0 RT : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-003 Rev.0 UT : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-004 Rev.0 Weld Plan : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J01-005 Rev.01 Weld repair : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-005 Rev.0 Hardness : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-006 Rev.01 PAUT : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-008 Rev.0 Heat Treatment : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J03-001 Rev.01 Pneumatic : J21P19-D1JCR-MES002-TPD-P-02-A-C301-K02-002 Rev.01 Helium Leak : J21P19-D1JCR-MES002-TPD-P-02-A-C301-K01-001 Rev.0 Hydrostatic Test : J21P19-D1JCR-MES002-TPD-P-02-A-C301-K02-001 Rev.0 Nitrogen Purging : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J02-007 Rev.01 Painting : J21P19-D1JCR-MES002-TPD-P-02-A-C301-J04-001 Rev.01 Packing and storage : J21P19-D1JCR-MES002-TPD-P-02-A-C301-M02-001 Rev.01 | LPT : PECPL/PT/001 Rev.11, RT : PECPL/RT/001 Rev.12, UT : PECPL/UT/001 Rev.15, Weld Plan : PE/WM/1793/05 Rev.01, Weld repair : PECPL/WRP/001 Rev.07, Hardness : PECPL/1793/Hardness/001 Rev.01, PAUT : PECPL/PAUT/001 Rev.0, Heat treatment : PECPL/1793/HT/001 Rev.1, Pneumatic Test : PECPL/1793/Pneumatic/001 Rev.1, Heilum Leak : PECPL/1793/HLT /001 Rev.0, Hydrostatic Test : PECPL/1793/Hydro/001 Rev.0, Nitrogen Purging : PECPL/1793/NP/001 Rev.01, Painting : PECPL/1793/Painting /001 Rev.01, Packing and storage: PECPL/1793/Packing/001 Rev.01 | Approved by T.EN in code.03.
5 | Datasheet(s) | NIL | NIL | NIL
6 | Others (Specify) | NIL | NIL | NIL

## Stages Witnessed
Stages Witnessed
ITP Sl No.: 4.0 - Pre - Inspection meeting attended along with PECPL representatives (Project, Design, QA & QC) and along with RIL representatives over Conference call for USG Depropanizer Feed Chiller.
ITP Sl.No.: 6.1, 6.3, 6.4 & 6.5 - Witnessed Material Identification was carried out on offered CS (Plates) and LTCS (STD Forgings, Non STD Forgings & Seamless tubes) correlated with manufacturer test certificate verified Original marking, Manufacturer name/Logo, Heat number, Material grade, size and Thickness – Found satisfactory.
ITP Sl.No.: 6.1 - Each Part identification, check test coupon and Production test coupon for CS (Plates) identified with TUV hard stamp near Heat Number - Found satisfactory.
ITP Sl.No.: 6.3 & 6.4 - Each Part identification for LTCS (STD Forgings & Non STD Forgings) identified with TUV hard stamp near Heat Number - Found satisfactory.
ITP Sl.No.: 7.3 - Witnessed Mechanical testing of test coupon in Normalized Condition Shell dish - Found satisfactory with respect to Material standard and approved drawing.
ITP Sl.No.: 7.4 - Visual and dimensional inspection was carried out on offered Shell dish head After Post forming Heat Treatment, verified (Total height, Inner diameter, Thickness, Profile Check & Template (Internal & external)) – Found within acceptable tolerance as per approved drawing.
ITP Sl.No.: 7.4 - Witnessed LPT was carried out on both inside/outside surface of Knuckle radius, Straight Face and Bevel edges of Shell dish head After Post forming Heat Treatment – No surface defects were observed.
ITP Sl.No.: 7.4 - Witnessed Hardness test was carried out on offered Shell dish head After Post forming Heat Treatment - Value are within 200 BHN with respect to Hardness Procedure.
ITP Sl.No.: 8.1 - Witnessed Visual and Final dimensional inspection was carried out on offered cones after forming, verified (Total height, Inner diameter, Ovality, Thickness, Profile Check & Template) – Found within acceptable tolerance as per approved drawing.
ITP Sl.No.: 8.1 - Witnessed LPT was carried out on both inside/outside surface of Knuckle radius and Bevel edges of cones after forming – No Surface defects were Noticed.
ITP Sl.No.: 8.1 - Witnessed Hardness test was carried out on offered cones after forming - Value are within 200 BHN with respect to Hardness Procedure.
ITP Sl.No.: 9.6, 10.2 & 10.4 – Random witnessed DPT on final weld of Branch Nozzle with main Nozzle, Shell L.S & C.S, Main Nozzle to Shell/channel assembly – No Surface defects were Noticed.
ITP Sl.No : 10.7 - Production Test coupon testing witnessed for Shell Assembly for each WPS – Found Acceptable.
ITP Sl.No : 10.8 – Witnessed Visual and dimensional inspection was carried out on offered Shell assembly and Channel Assembly – Found within acceptable tolerance as per approved drawing.
ITP Sl.No.: 11.3 – Random witnessed Hardness test was carried out on offered Channel Assembly After PWHT - Value are within 200 BHN with respect to Hardness Procedure.
ITP Sl.No : 11.4 - Production Test coupon testing witnessed for Channel Assembly After PWHT for each WPS – Found Acceptable.
ITP Sl.No : 11.5 – Witnessed Visual and dimensional inspection was carried out on offered Channel Assembly After PWHT – Found within acceptable tolerance as per approved drawing.
ITP Sl.No : 12.1 - Witnessed Visual and Dimensional inspection was carried out for offered Stationary Tubesheet after machining and drilling – Found within tolerance with respect to approved drawing.
ITP Sl.No : 12.3 - Witnessed final dimension, Orientation and BOM checking was carried out for offered Tube Bundle Skeleton assembly - Found within acceptable tolerance with respect to approved drawing.
ITP Sl.No : 12.4 - Witnessed DPT was carried out on Stationary Tubesheet after Root and Final Welding - No indication were observed.
ITP SL.No: 12.5 - Witnessed Pneumatic test, Pressure at 1.25 Kg/cm2 (g) was carried out on Tube to Tube sheet joint after Final Welding for Stationary Tubesheet - By applying soap solution no leakage was noticed with respect to test Procedure.
ITP Sl.No : 12.6 - Random Witnessed Tube to Tubesheet Joint expansion was carried out on Stationary Tubesheet - Found within Percentage of thinning (2% to 3%) and Expansion length are within acceptable limits.
ITP Sl.No : 12.8 - Witnessed Helium leak test (sniffer probe method) for duration of 30 minutes holding time was carried out on Tube to Tubesheet joint after expansion of Stationary Tubesheet - Leak rate are within limits with respect to approved procedure.
ITP Sl.No : 12.9 - Visual and Final Dimensional inspection in assembled condition was carried out on offered USG Depropanizer Feed Chiller - Found within acceptable tolerance with respect to approved drawing.
ITP Sl.No : 12.12 - Visual check, dimension and Quantity verification done on offered Commissioning Spares and Loose items with respect to approved drawing – Found satisfactory.
ITP Sl.No : 12.12 - Witnessed PMI test was carried out on offered Fasteners (L7, B7 & SS Grade) and S.S Gaskets – Test results meets the approved drawing requirement.
ITP Sl.No : 13.1 - Witnessed Open Bundle hydrostatic test, Pressure at 61.212 Kg/cm2 (g) for duration of 60 Minutes holding time at ambient condition with respect to approved procedure and Drawing – No Leakage or Pressure drop were noticed during testing.
ITP Sl.No : 13.2 - Witnessed Shell Side hydrostatic test Including Tube to Tubesheet Joint, Pressure at 25.214 Kg/cm2 (g) for duration of 60 Minutes holding time at ambient condition with respect to approved procedure and Drawing – No Leakage or Pressure drop were noticed during testing.
Witnessed Helium leak test (sniffer probe method) for duration of 30 minutes holding time was carried out on Tube to Tubesheet joint of Stationary Tubesheet after Shell Side hydrostatic test - Leak rate are within limits with respect to approved procedure.
ITP Sl.No : 13.3 - Witnessed Final Tube Side Hydrostatic test, Pressure at 61.212 Kg/cm2 (g) for duration of 60 Minutes holding time in ambient condition with respect to approved procedure and Drawing – No Leakage or Pressure drop were noticed during testing.
ITP Sl.No : 13.4 - Witnessed Draining and Drying was carried out by passing Hot air on both Shell side and Tube side – The observed relative humidity of hot air is less than 50% with respect to the approved procedure, which was found satisfactory.
ITP Sl.No : 14.1 - Witnessed Surface preparation (Blast cleaning) surface roughness, profile, finish and salt contamination was carried out on offered USG Depropanizer Feed Chiller – Found acceptable.
ITP Sl.No : 14.1 – Witnessed Paint DFT check at random spot was carried out on offered USG Depropanizer Feed Chiller – Observed DFT are within acceptable limits with respect to approved procedure.
ITP Sl.No : 14.1 – Visual examination, RAL shade and Adhesion test (Tape Test) was checked at random location for offered USG Depropanizer Feed Chiller – Found satisfactory with respect to approved procedure.
ITP Sl.No : 14.1 - Witnessed Adhesion test (Pull Off Test (On Test plate)) – Adhesive strength meets the Minimum requirement with respect to approved Procedure.
ITP Sl.No : 15.1 - Witnessed the stamping of equipment, rub-off and Name Plate stamping done on USG Depropanizer Feed Chiller correlated with the approved drawing and were found acceptable.
ITP Sl.No : 15.3 - Witnessed Final Packing & Marking physically verified as per Packing list - Found satisfactory.

## Document reviewed
Document reviewed
ITP Sl.No : 3.0 - Verified RIL approved document (NDE Procedure, PAUT Procedure, Weld Repair Procedure, heat treatment Procedure (PFHT/PWHT), Hydrostatic Procedure, Hardness Procedure, Pneumatic Procedure, Helium Procedure, Drying/Nitrogen Procedure, Painting procedure & Packing Procedure - Found in order.
ITP Sl.No : 5.1 & 5.2 - Verified Welding document (WPS/PQR/WPQ) – Found in order.
ITP Sl.No : 5.3 – Reviewed mock-up procedure for TTS Joint – Found in order.
ITP Sl.No : 6.1, 6.3, 6.4 & 6.5 - Reviewed Material consolidated report and Manufacturer Test Certificate (EN10204 Type 3.1) / LAB check report for offered CS (Plates) and Manufacturer Test Certificate (EN10204 Type 3.2) for LTCS (STD Forgings, Non STD Forgings & Seamless tubes) – Found to meets the Material specification, TDC and approved Drawing requirement.
ITP Sl.No : 6.6 - Reviewed Material consolidated report & Manufacturer test certificate (EN10204 Type 3.1) for Non-Pressure Parts – Found to meets the Material specification, TDC and approved Drawing requirement.
ITP Sl.No : 6.7 - Reviewed Material consolidated report & Manufacturer test certificate (EN10204 Type 3.2) for Fasteners and Gaskets – Found to meets the Material specification, TDC and approved Drawing requirement.
ITP Sl.No : 6.8 - Reviewed Welding Consumables consolidated report & Filler wire/ Flux/electrode batch test certificate – Found in order.
ITP Sl.No : 7.1 - Reviewed Visual and Dimension report for Shell dish after forming – Found in order.
ITP Sl.No : 7.2 - Reviewed Normalizing Heat treatment chart for Shell dish after forming – Found in order.
ITP Sl.No : 9.3, 9.5, 10.1 & 10.3 - Reviewed Nozzle Neck with Flange Fit-up report, Main Nozzle with Branch Nozzle Fit-up report, Shell (L.S & C.S) Fitup report and Main Nozzle to Shell/channel assembly – Found in order.
ITP Sl.No : 10.1 & 10.3 – Reviewed consolidated report & Bevel Edge DPT report for Shell L.S & C.S and Main Nozzle to Shell/channel assembly – Found in order.
ITP Sl.No : 9.4, 9.6 & 10.2 - Reviewed consolidated report & Root weld DPT report for Nozzle Neck with Flange, Branch Nozzle with main Nozzle and Shell Port to Cone/ Flange – Found in order.
ITP Sl.No : 10.2 & 10.4 - Reviewed consolidated report & Root Back Gouging weld DPT report for Shell L.S & C.S and Main Nozzle to Shell/channel assembly.
ITP Sl.No : 9.4, 9.6, 10.2, 10.4, 10.5 & 10.6 - Reviewed consolidated report & Balance Final weld DPT report for Nozzle Neck with Flange, Branch Nozzle with main Nozzle, Shell L.S & C.S, Main Nozzle to Shell/channel assembly, Internal/ External attachment weld on Shell/channel assembly and Temporary attachment weld on Shell/channel assembly – Found in order.
Reviewed Final weld DPT report for Load bearing welds of Lifting Lug and Support weld – Found in order.
Reviewed UT report for Shell Beneath of Lifting Lug – Found in order.
ITP Sl.No : 9.4 & 10.2 – Reviewed consolidated report & RT Report/Films for Nozzle Neck with Flange & Shell L.S/C.S – No Relevant indication were noticed.
ITP Sl.No : 11.1 - Reviewed Post weld Heat treatment chart for Channel Assembly along with PTC – Found in order.
ITP Sl.No : 11.2 - Reviewed Final weld DPT report for Channel Assembly After PWHT – Found in order.
ITP Sl.No : 11.2 - Reviewed consolidated report & RT Report/Films for Channel Assembly After PWHT – No Relevant indication were noticed.
ITP Sl.No : 12.2 - Reviewed Dimension report for Support Plate as per approved drawing – Found in order.
ITP Sl.No : 12.7 - Reviewed DPT report of Tube to Tubesheet joint after expansion of Stationary Tubesheet - Found in order.
ITP Sl.No : 14.2 - Reviewed Nitrogen Purging report of USG Depropanizer Feed Chiller - Found in order.
ITP Sl.No : 15.2 - Reviewed As-Built drawing for USG Depropanizer Feed Chiller – Found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Digital Pressure Gauge | 0 to 700 Bar | PE-I-DIGPIG-07 | 16.10.2023 | Tii230417-1-1 | YES |  | Yes
2 | Digital Pressure Gauge | 0 to 700 Bar | PE-I-DIGPIG-05 | 16.10.2023 | Tii230417-1-2 | YES |  | No
3 | Pressure Gauge | 0 to 106 kg/cm2 (g) | PE-II/PRG/611 | 03.10.2023 | CRMTL/01/423100066-A25 | YES
4 | Pressure Gauge | 0 to 106 kg/cm2 (g) | PE-II/PRG/612 | 03.10.2023 | CRMTL/01/423100066-A26 | YES
5 | Pressure Gauge | 0 to 106 kg/cm2 (g) | PE-II/PRG/613 | 03.10.2023 | CRMTL/01/423100066-A27 | YES
6 | Pressure Gauge | 0 to 106 kg/cm2 (g) | PE-II/PRG/614 | 03.10.2023 | CRMTL/01/423100066-A28 | YES
Type equation here.
"Type equation here."

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
PECPL to Offer all Witness/Review Stage to TUV India as per ITP.

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: