## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number | EMAIL ON DT. -
Project Name & Location
Client Name | KLJ PETROPLAST LTD. JHAGADIA
End User Name | KLJ PETROPLAST LTD. JHAGADIA
DEC / PMC / EPC Name | NOT APPLICABLE
DEC / PMC / EPC Number | NOT APPLICABLE
Vendor Name | NUBERG ENGINEERING LTD.
PO Number (Client PO on Vendor) | IntPO/KPPL/CG/JH/21-22/0102, 08.11.2021.
Sub Vendor | NOT APPLICABLE
PO Number (Vendor PO on Sub Vendor) | NOT APPLICABLE
Inspection Location | NUBERG ENGINEERING LTD., JHAGADIA GIDC.
Inspection Date(s)

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
4 | * CLIENT PROJECT NO. - 1219. * NUBERG PROJECT NO. - 1224. | TAG NO. T-1006, EXPANSION TANK, | number | 1 | 1 | 1 | 1 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | Not Applicable | 1. FOR, TAG NO(s). - T-1006 & T-1007, - NBEL/ITP/1224/001, REV.00, DT. 02.02.2022. | Approved by KLJ
3 | Drawing(s) | Not Applicable | - VENDOR DRAWING NO(s) AS MENTIONED BELOW, 1). FOR, T-1006, 1224-45-EMF-05-01-0, REV.02, (GA, CODE-1 Approved). | Approved with comment by M/s. Quanta Process Pvt. Ltd.
4 | Procedure(s) | Not Applicable | - NBEL/NDE/01, REV.0 - NDE PROCEDURE, FOR LPT(REV.05), RT(REV.09) & UT(REV.04). - HYDRO TESTING AND PNEUMATIC TEST - NBEL/HYDROTEST & PNEUMATIC TEST/01, REV.0. DT. 05.01.2022 | APPROVED BY KLJ ON 05.01.2022.
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
ITP Sr. No. 3.1, Tag No.: T-1006, Raw material identification of pressure parts (main shell, dished end, R F Pad & Fab. Nozzle neck plates, pipes, flanges, fittings. – Found to meet the approved drawing, applicable material specification & project specification requirements.
ITP Sr. No. 4.1.1, Tag No.: T-1006, Final Dimensional inspection of Top & Bottom 2:1 Ellipsoidal dished end carried out after forming. - Found to meet the drawing and code requirement.
ITP Sr. No. 4.1.3, Tag No.: T-1006, Penetrant test from inside & outside of knuckle portion, S.F. and WEP witnessed. – No surface indication observed.
ITP Sr. No. 4.2.4, Tag No.: T-1006, Weld visual inspection of all L/S BW joints are carried out. - No major significant indication were observed.
ITP Sr. No. 4.2.5, Tag No.: T-1006, Radiography films of all L/S BW joints (As per approved drawing scope) reviewed. - No significant indication were observed.
ITP Sr. No. 4.2.9, Tag No.: T-1006, Weld visual inspection of all C/S BW joints are carried out. - No major significant indication were observed.
ITP Sr. No. 4.2.10, Tag No.: T-1006, Radiography films of all C/S BW joints (As per approved drawing scope) reviewed. - No significant indication were observed.
ITP Sr. No. 4.3.9, Tag No.: T-1006, R F pad pneumatic test of nozzles (F1, F2, F3, P, SV, V, D, LT, S1, MH1 & MH2) at a pressure of 1.50 kg/cm² (g) and checked with soap solution from inside & outside of welding. - No leakage observed during the testing period.
ITP Sr. No. 6.1, Tag No.: T-1006, Visual inspection of equipment from inside & outside during final dimensional inspection carried out. - No major surface imperfections were observed.
ITP Sr. No. 6.2, Tag No.: T-1006, Final Dimension inspection of equipment carried out after completion of all fabrication activities. - Found to meet Drawing Requirements.
ITP Sr. No. 7.1, Tag No.: T-1006, Hydro test of complete equipment witnessed at a pressure of 3.4 KG/CM2 (G) in horizontal position [ Required Test Pressure : 2.8 KG/CM2 (G) for horizontal position ] for one hour holding period. No leakage or pressure drop and no visible permanent distortion observed.
ITP Sr. No. 9.2, Tag No.: T-1006, Name plate verified as per drawing. - Found in order and stamped as “TUV ROUND STAMP".
All measuring instruments / equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
Approved QAP No. NBEL/ITP/1224/001, REV.00, DT.02.02.2022.
ITP Sr. No. 1.3, 1.4 & 1.5, Drawing, NDE procedures and QC procedures. Found in order.
ITP Sr. No. 2.1 & 2.3, WPS/PQR, WPQ, NDT procedures and NDE personal & Welder qualification records. Found in order.
ITP Sr. No. 2.2, Welding consumables batch test certificates. Found to meet the code requirement.
Weld map / NDT plan. Found to meet the drawing requirement.
ITP Sr. No. 3.1, 3.2 & 3.3, Raw material test certificates / traceability and check test reports of pressure parts, non-pressure parts and parts directly attached to pressure parts as declared by manufacturer. Found to meet the respective material specification, code and additional project specification requirement.
ITP Sr. No. 4.2.1 & 4.2.6, Main shell sections long seam & circumferential seam set up inspection reports. Found as per drawing.
ITP Sr. No. 4.2.3 & 4.2.8, Penetrant test summary of all LS & CS bevel edges after back chipping. Found in order.
ITP Sr. No. 4.2.5 & 4.2.10, Radiography summary sheet verified with RT / NDT Sketch and radiography reports. Found in order.
ITP Sr. No. 4.3.1, Nozzle orientation marking on main shell & top / bottom dished end. Found as per drawing.
ITP Sr. No. 4.3.2 & 4.3.6, Nozzle pipe to flange set up and nozzle neck to main shell, top & bottom dished end set up inspection reports. Found as per drawing.
ITP Sr. No. 4.3.5 & 4.3.8, Weld visual inspection of Nozzle pipe to flange joint and nozzle neck to main shell, top / bottom dished end joint inspection reports. Found in order.
ITP Sr. No. 7.1, Pressure gauge calibration certificates reviewed. Found in order.
ITP Sr. No. 8.1, Painting on CS Parts report reviewed. Found as per approved KLJ Painting specification requirement.
ITP Sr. No. 9.1, Material heat chart for pressure parts, non-pressure parts and parts directly attached to pressure parts. Found to meet the drawing, material code and project specification requirement.
ITP Sr. No. 9.1, All the documents verified as per approved ITP. Found in order.
Internal inspection report of DPT Inspection carried out on all fillet weld joint which is attached directly with pressure parts after final hydro testing. - Found as per general note instruction of GA Drawing.
All pressure gauge instruments / equipment were verified for continued suitability for intended use, proper identification, and calibration status found satisfactory.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern
CLIENT CONFIRMATION / ACCEPTANCE REGARDING "TUV" HARD STAMP ARE NOT VERIFIED / NOT FOUND ON TOP DISHED END NOZZLE R.F.PADS DURING FINAL DIMENSIONAL INSPECTION ISSUE RECEIVED THROUGH MAIL ON DT. 30.07.2022.

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: