## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 050104138820/33
SAP number | 8118675586
Notification Number | Mail dated- 18.04.2022
Project Name & Location | LL1003 / SEZ-4
Client Name | JUBILANT INGREVIA LIMITED (Unit -4)
End User Name | Not Applicable
DEC / PMC / EPC Name | Not Applicable
DEC / PMC / EPC Number | Not Applicable
Vendor Name | CHEM PROCESS SYSTEMS PVT LTD
PO Number (Client PO on Vendor) | 160083 -Dated- 07/02/2022
Sub Vendor | Not Applicable
PO Number (Vendor PO on Sub Vendor) | Not Applicable
Inspection Location | 15 Natraj Industrial Estate, Sanand Viramgam Highway, Sanand 382170. Ahmedabad
Inspection Date(s) | 21.04.2022 & 22.04.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 950672385E | Ejector System- Multi stage consist of Y Stage steam Jet Ejector, Z Stage steam ejector, Hogger Ejector and Inter & After Condensers | each | 1 | 1 | 1 | 1 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not applicable | Not applicable | Not applicable
2 | QAP/ITP/QCP | Not Applicable | EVS-1883-QAP, REVISION : R0, DATE : 11.02.2022 | Approved by Client dt 23.04.2022
3 | Drawing(s) | Not Applicable | (1) EVS-1883-GA-VS, REVISION : 01, DATE : 23.02.2022- GA DRAWING (2) EVS-1883-P & ID-VS, REVISION : 01, DATE : 23.02.2022- P & ID DRAWING | Approved by Client through mail dated- 23.02.2022
4 | Procedure(s) | Not Applicable | Not Applicable | Not applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | PO Annexure | Not Applicable | Provided by client

## Stages Witnessed
Stages Witnessed
ITP Stage Sr. No.: B.2- Witnessed Shell side Hydro test of Shell & Tube Type Inter Condenser & After Condenser at 2 kg/cm2-Neither Leakage nor pressure drop observed during 1 hour holding time-Found satisfactory.
ITP Stage Sr. No.: B.4- Witnessed Channel side Hydro test of Shell & Tube Type Inter & After Condenser at 5 kg/cm2-Neither Leakage nor pressure drop observed during 1 hour holding time-Found satisfactory.
ITP Stage Sr. No.: C.2- Witnessed Body side Hydro test of Y stage steam jet Ejector & Z stage steam jet Ejector & Hogger Ejector at 2 kg/cm2-Neither Leakage nor pressure drop observed during 1 hour holding time-Found satisfactory.
ITP Stage Sr. No.: C.2- Witnessed Motive side Hydro test of Y stage steam jet Ejector & Z stage steam jet Ejector & Hogger Ejector at 25.4 kg/cm2-Neither Leakage nor pressure drop observed during 1 hour holding time-Found satisfactory.
ITP Stage Sr. No.: B.3 & C 1 Witnessed Final Skid Assembly Dimension & Visual Inspection (external surface only) for offered Ejector System w.r.t. approved GA drawing Dimensions - found as per approved drawing. Visually found satisfactory.

## Document reviewed
Document reviewed
ITP Stage Sr. No.: B1 - Reviewed Photocopy of Material Test certificates as declared by vendor for the Main shell , Channel shell, Tube, Tube sheet, Body Flange , End Cover - Found in order to meet the requirements of the material specification.
Calibration certificate of Instruments used for inspection are reviewed and found having valid calibration at the time of inspection.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
| Measuring Tape | 0 TO 5 MTR | MT5/1 | 16.03.2023 | NCQC-M/170322/05,Dated-17.03.2022 | Yes | No | Yes
| Pressure Gauge | 0 to 4.2 Kg/cm2 | EXL-210295J | 02.09.2022 | 892098 Dated-03.09.2021 | No | Yes | No
| Pressure Gauge | 0 to 4.2 Kg/cm2 | EXL-210296J | 02.09.2022 | 892099- Dated-03.09.2021 | No | Yes
| Pressure Gauge | 0 to 4.2 Kg/cm2 | EXL-210292J | 02.09.2022 | 892095 Dated-03.09.2021 | No | Yes
| Pressure Gauge | 0 to 4.2 Kg/cm2 | EXL-210298J | 02.09.2022 | 892101 Dated-03.09.2021 | No | Yes
| Pressure Gauge | 0 to 4 Kg/cm2 | 21TG-163 | 22.07.2022 | 2107163 Dated-23.07.2021 | No | Yes
| Pressure Gauge | 0 to 4.2 Kg/cm2 | 20TE-577 | 06.08.2022 | PG/21-22/11 Dated-07.08.2021 | No | Yes
| Pressure Gauge | 0 to 42 Kg/cm2 | 21TG-110 | 22.07.2022 | 2107110 Dated-23.07.2021 | No | Yes
| Pressure Gauge | 0 to 42 Kg/cm2 | EXL-214074A | 07.01.2023 | PG/2223/115 Dated-08.01.2022 | No | Yes
| Pressure Gauge | 0 to 16 Kg/cm2 | EXL-214073A | 07.01.2023 | PG/22-23/38 Dated-08.01.2022 | No | Yes
| Pressure Gauge | 0 to 16 Kg/cm2 | 21TG-134 | 22.07.2022 | 2107134, Dated-23.07.2021 | No | Yes
| Measuring Tape | 0 TO 15 MTR | MT15/1 | 16.03.2023 | NCQC-M/170322/03,Dated-17.03.2022 | Yes | No
| Pressure Gauge | 0 to 10 Kg/cm2 | EXL-210306J | 02.09.2022 | 892109, Dated-03.09.2021 | No | Yes
| Pressure Gauge | 0 to 10 Kg/cm2 | EXL-214068A | 07.08.2022 | PG/2122/109 Dated-08.08.2021 | No | Yes
| Pressure Gauge | 0 to 10 Kg/cm2 | 20TE-592 | 07.08.2022 | PG/2122/35 Dated-08.08.2021 | No | Yes
| Pressure Gauge | 0 to 10 Kg/cm2 | 21TG-138 | 22.07.2022 | 2107138, Dated-23.07.2021 | No | Yes
| Pressure Gauge | 0 to 16 Kg/cm2 | 21TG-128 | 22.07.2022 | 2107128, Dated-23.07.2021 | No | Yes
| Pressure Gauge | 0 to 16 Kg/cm2 | 21TG-129 | 22.07.2022 | 2107129, Dated-23.07.2021 | No | Yes

## Areas of concerns
Areas Of Concern
Vendor is offering Dimension, Hydro test , document as per Vendor Internal drawing due to attached P & ID & GA Drawing is not showing hydro test pressure & Dimension details (Elevation, Projection & etc ). Vendor is not Provided internal drawing for approval- Same as informed by client through mail dated 21.04.2022.
QAP is not approved by client.

## Pending Activities
Pending Activities from this visit
None

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
None
Identification of Inspected Item(s):
None
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Offered Stages are accepted Subjected to Clear/close area of concern points.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: