## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number | 8116951448
Notification Number | Email Dt 25.04.2022
Project Name & Location | DDP JMD SEZ Site
Client Name | Reliance Industries Limited
End User Name | Reliance Industries Limited
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name | M/s. Boldrocchi India Pvt Ltd, Irungatukottai.
PO Number (Client PO on Vendor) | HPRJ/MWL/7753149 Dt.13.01.2021 (BI Job No : VR00724)
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | M/s. Boldrocchi India Pvt Ltd, Irungatukottai.
Inspection Date(s) | 11.04.2023

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 |  | Weighing Plot form Scale, Tag No: WG-HAND101 ,P& ID 418352-MMD-00-XX-DR-PR-0029 Rev C09 | each | 1 | 1 | 1 | 1 | number
2 |  | Weighing Plot form Scale, Tag No: WG-PUHAND101 ,P& ID 418352-MMD-00-XX-DR-PR-0030 Rev C08 | each | 1 | 1 | 1 | 1 | meter
3 |  | Weighing Plot form Scale, Tag No: WG-HANDRE3 , P& ID 418352-MMD-00-XX-DR-PR-0032 Rev C08 | each | 1 | 1 | 1 | 1 | km
4 |  | Weighing Plot form Scale, Tag No: WG-HANDRE4 , P& ID 418352-MMD-00-XX-DR-PR-0034 Rev C08 | each | 1 | 1 | 1 | 1 | meter (number)
5 |  | Weight Transmiter. Tag No:WIT-500101,For equipment: MP-50, P& ID 418352-MMD-00-XX-DR-PR-0029 Rev C09 | each | 1 | 1 | 1 | 1 | km (number)
6 |  | Weight Transmiter. Tag No:WIT-500201,For equipment: CP-50, P& ID 418352-MMD-00-XX-DR-PR-0029 Rev C09 | each | 1 | 1 | 1 | 1 | each
7 |  | Weight Transmiter. Tag No:WIT-590101,For equipment: MP-59,P& ID 418352-MMD-00-XX-DR-PR-0030 Rev C08 | each | 1 | 1 | 1 | 1 | Piece
8 |  | Weight Transmiter. Tag No:WIT-590201,For equipment: CP-59,P& ID 418352-MMD-00-XX-DR-PR-0030 Rev C08 | each | 1 | 1 | 1 | 1 | Test sample
9 |  | Weight Transmiter. Tag No:WIT-509001,For equipment: CT-5090,P& ID 418352-MMD-00-XX-DR-PR-0029 Rev C09 | each | 1 | 1 | 1 | 1 | AU - All Unit
10 |  | Weight Transmiter. Tag No:WIT-509101,For equipment: CT-5091,P& ID 418352-MMD-00-XX-DR-PR-0030 Rev C08 | each | 1 | 1 | 1 | 1 | lot
11 |  | Weight Transmiter. Tag No:WIT-MP3-101, For equipment: MP-3.P& ID 418352-MMD-00-XX-DR-PR-0032 Rev C08 | each | 1 | 1 | 1 | 1 | Set
12 |  | Weight Transmiter. Tag No:WIT-CP3-201 ,For equipment No.CP-3,P& ID 418352-MMD-00-XX-DR-PR-0032 Rev C08 | each | 1 | 1 | 1 | 1 | Running Meter
13 |  | Weight Transmiter. Tag No:WIT-MP1-101 For equipment No.MP-1,P& ID 418352-MMD-00-XX-DR-PR-0033 Rev C08 | each | 1 | 1 | 1 | 1 | kg
14 |  | Weight Transmiter. Tag No:WIT-CP1-201 For equipment No.CP-1.P& ID 418352-MMD-00-XX-DR-PR-0033 Rev C08 | each | 1 | 1 | 1 | 1 | metric ton (tonne)
15 |  | Weight Transmiter. Tag No:WIT-MP4-101 For equipment No.MP-4,P& ID 418352-MMD-00-XX-DR-PR-0034 Rev C08 | each | 1 | 1 | 1 | 1 | ton
16 |  | Weight Transmiter. Tag No:WIT-CP4-201 For equipment No.CP-4.P& ID 418352-MMD-00-XX-DR-PR-0034 Rev C08 | each | 1 | 1 | 1 | 1 | cubic millimetre
17 |  | Weight Transmiter. Tag No:WIT-MP2-101 For equipment No.MP-2,P& ID 418352-MMD-00-XX-DR-PR-0035 Rev C08 | each | 1 | 1 | 1 | 1 | cubic centimeter
18 |  | Weight Transmiter. Tag No:WIT-CP2-201 For equipment No.CP-2,P& ID 418352-MMD-00-XX-DR-PR-0035 Rev C08 | each | 1 | 1 | 1 | 1 | cubic meter
19 |  | Weight Transmiter. Tag No:WIT-TMCMX For equipment No.TM-CMX,P& ID 418352-MMD-00-XX-DR-PR-0043 Rev C02 | each | 1 | 1 | 1 | 1 | cubic inch
20 |  | Weight Transmiter. Tag No:WIT-TMDMX For equipment No.TM-DMX.P& ID 418352-MMD-00-XX-DR-PR-0043 Rev C02 | each | 1 | 1 | 1 | 1 | cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | NIL | NIL | Not applicable
2 | QAP/ITP/QCP | NIL | PMIL/TWS/QAP Rev 0 | Approved by Ideal Chemi plast
3 | Drawing(s) | Nil | PM-PFS/650/650/GA/DIM/001 REV 01, TWS/MECH/GA/26597/NCL/PMIPL/004 Rev 00,TWS/MECH/GA/26597/NCL/PMIPL/004 Rev 00,TWS/MECH/GA/ICPL/PMIPL/001 Rev 00,TWS/MECH/GA/ICPL/PMIPL/002 Rev 00,TWS/MECH/GA/ICPL/PMIPL/003 Rev 00,TWS/MECH/GA/ICPL/PMIPL/006 Rev 00. | Approved by Mott McDonald
4 | Procedure(s)
5 | Datasheet(s)
6 | Others (Specify)

## Stages Witnessed
Stages Witnessed
ITP SL No.1 . Visual inspection carriedout for 100 % of offered Mounting assembly,Digital Weight Indicator with EXD ,Loadcells and Junction box cables-Found no injurious defects observed.
ITP SL No.2 Dimensional inspection of completed platform scale and mouting assembly carriedout as per approved drawings -Found acceptable
ITP SL No.3 Functional test ( Electrical simulation test weight verification ) carriedout for 10 % random selected indicator ,load cell ( input and output Impedence ) ,Platform scale calibration with calibrated weight as per approved QAP -Found acceptable and reports attested for records.

## Document reviewed
Document reviewed
ITP SL NO 4.0 Reviewed Wether proof /PESO certificate for load cell , JB,s and EXD enclosure for weight indicator-Found inorder
ITP Sl No.:5.0 Reviewed test certificate for Load mount, load cell ,indicator EXD, JBs, calibration certificate for plat form scale - Found acceptable and reports attested for records.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
| Pressure Gauge |  | 744 | 30.12.2022 | 2021-22/ CFC/ 2286 1 date: 30.12.2021 |  |  | Yes
1 | Measuring Tape | 0 to 5 mtrs | 126 | 05.10.2023 | TC-10-22/ATL/185501 | Yes |  | No
2 | Digital multimeter | 1-1000V | 8015243 | 06.09.2023 | TC-09-22/ATL/124501 | Yes
3 | Vernier Caliper | 0-300 mm | 18041151 | 17.02.2024 | PC-02-23/ATL/0703-02 | Yes
4 | standard weight | 20 kgs | 220708-08 | 08.07.2023 | HT/CC/220708-08/002 | Yes

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
NIL
Identification of Inspected Item(s):
Not Applicable
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
NDT DP test acceptable ,Hydrotest result subject to client acceptance for testing with rubber gaskets.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: