## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 010101145721/20
SAP number | 8118997801
Notification Number | DEM/-KPTL/BALL/SVITA/MECON/2021-22/04 Email Dated - 24.01.2022
Project Name & Location | North East Gas Grid (NEGG) Project - Part A
Client Name | Kalpataru Power Transmission Limited (31127)
End User Name | Indradhanush Gas Grid Limited (36014)
DEC / PMC / EPC Name | Mecon Ltd Delhi
DEC / PMC / EPC Number | Not Applicable
Vendor Name | DEMBLA VALVES LIMITED (38243)
PO Number (Client PO on Vendor) | 2300122188 Dated - 10.06.2021
Sub Vendor | Not Applicable
PO Number (Vendor PO on Sub Vendor) | Not Applicable
Inspection Location | A/8 Arham Logicpark Village - Valishind, Mumbai Nashik National Highway ( NH3 ) Taluka : Bhiwandi, District : Thane, State : Maharashtra - 421302
Inspection Date(s) | 27.01.2022, 28.01.2022, 29.01.2022 & 31.01.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | I3092864059 | 1 INCH, GATE VALVE CL.800 A182 GR F304/HF SW BB, OS&Y BY MFR/API 602/ASME B16.11 HANDWHEEL Comodity Code: AXCT303_F_1 Tag no: 51045 (V-21370 & V-21371) Valve Sr no.: FN0446 To FN0447 Niton MTC No.: NVI/A2001/D9711/2022 | number | 2 | 2 | 2 | 2 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | Not Applicable | ITP-AXHB204 Rev.00 | Final Approved By TUV & TOYO
3 | Drawing(s) | 6399-TOYO-PKG-AXCT303F-0001 Rev.A | NV/I080/A2001-01 Rev.0 | Approved in code A by TOYO
4 | Procedure(s) | Not Applicable | NVI/HPT/QC-HP1, R0, NVI/PMI/01, R1 | Reviewed By TUV
5 | Datasheet(s) | A-6399-PI-5107 Rev.C | Not Applicable | Client Doc.
6 | Others (Specify) | EIL technical notes1) 6-44-0052, Rev. 7 2) 6-81-0001, Rev.3 | Not Applicable | EIL Document

## Stages Witnessed
Stages Witnessed
ITP Stage No 7: Shell Hhydrostatic test as per approved drawings & ITP on 10% randomly selected qty from each PO line item–No leakage or pressure drop observed during holding time
ITP Stage No 7: Back Seat Hhydrostatic test as per approved drawings & ITP on 10% randomly selected qty from each PO line item–No leakage or pressure drop observed during holding time
ITP Stage No 7: Seat Hhydrostatic test (Both side) as per approved drawings & ITP on 10% randomly selected qty from each PO line item–No leakage or pressure drop observed during holding time
ITP Stage No 7: Seat Pneumatic test (Both side) as per approved drawings & ITP on 10% randomly selected qty from each PO line item–No leakage or pressure drop observed during holding time
ITP Stage No 8:Valve functional test (Manually Open-Close) checked on 10% randomly selected qty from each PO line item – Smooth operation observed at the time of inspection.
ITP Stage No 9: 100% Visual checked (Outside & inside feasible area) condition on offered Qty.-Found free from cracks, Dent, burr & obvious defects at the time of inspection.
ITP Stage No 9:Dimension checked (F-F, Socket Depth, dia., Stem dia, Shell Thickness etc) on 10% randomly selected qty from each PO line item-Found to meet QAP & approved drawing requirement.
ITP Stage No 10: PMI test carried out (Body, bonnet, Wedge, Stem, Fasteners Etc.) during strip test & final accessible area on 10% randomly selected qty from each PO line item-Found to meet material specification requirement
ITP Stage No 11: Strip test witnessed 1% per tag (min 1 number) on offered PO line item (FN0447)– Checked all trim material & condition of mating parts, stem & wear travel dimension and found acceptable
ITP Stage No 12: Marking checked on valve (Engraved/Hard Punch Mfg. Logo [NITON], Size, Class, Grade, Body & Adaptor Heat No, valve Sr no) & Tag verified as Mfr. Name, Type, Size, Pressure Class, Body, Trim, Seat, Valve Sr no., Mfg. std., & Valve Tag no, MFG. Year, Item Code, along with separate tag on 10% randomly selected Valve from offered PO line item- Found to meet ITP & drawing requirement
ITP Stage No 13: For identification, 10% Hydrostatic tested Valve has been hard double & rest with single stamp as "TUV Round stamp" on body & Bonnet joint near valve Sr. no. punched
All measuring Instruments/ Equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
ITP Stage No 2: WPS, PQR, WPQ verified-Found in order
ITP Stage No 3:Raw material test certificates for Body, Bonnet, Spindle, Wedge, Seat ring including IGC-E test report (As Applicable) declare by supplier –Found to meet ITP & material specification requirement
ITP Stage No 4: Manufacturer test certificates for Gaskets & Fasteners declare by supplier –Found to meet ITP & material specification requirement
ITP Stage No 6: Internal DP & UT test report declare by supplier –Found to meet ITP & material specification requirement
ITP Stage No 7 to 12 :Vendor submitted Visual, dimension, Pressure Test (Shell+Seat +Backseat Hydro, seat pneumatic test), Functional , PMI test, Strip test, UT report, DP test report on machining, Marking, Tagging repprt–Found to meet ITP, drawing & specification requirement
ITP Stage No 13: Manufacturer test certificates (NVI/A2001/D9711/2022) as per EN 10204:3.1 reviewed- Found to meet ITP, drawing & specification requirement
ITP Stage No 14:Preshipment inspection report declare by supplier –Found in order

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
PO Sr. No. 10 Valves provisionally hard stamped as " " for identification near manufacturer marking subjected to points mentioned in area of concrn column.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable subjected to manufacturer action on points mentioned in area of concern column.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: