## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number | 1
Project Name & Location
Client Name | Thermax ltd
End User Name | Thermax td
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | IGP II
PO Number (Client PO on Vendor) | 1000075650 Dt 15,02,2023
Sub Vendor
PO Number (Vendor PO on Sub Vendor)
Inspection Location
Inspection Date(s)

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
25 | NI00063373 | Gask,Octogonal,AlloySteel 5Cr,50mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 3 | 3 | 3 | 3 | number
26 | NI00063374 | Gask,Octogonal,AlloySteel 5Cr,80mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 9 | 9 | 9 | 9 | meter
34 | NI00074097 | Gask,Octogonal,AlloySteel 5Cr,450mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 9 | 9 | 9 | 9 | km
45 | NI00074108 | Gask,Octogonal,Soft iron,50mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 7 | 7 | 7 | 7 | meter (number)
46 | NI00074109 | Gask,Octogonal,Soft iron ,100mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 4 | 4 | 4 | 4 | km (number)
65 | NI00074093 | Gask,Octogonal,AlloySteel 5Cr,20mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 10 | 10 | 10 | 10 | each
66 | NI00074094 | Gask,Octogonal,AlloySteel 5Cr,100mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 4 | 4 | 4 | 4 | Piece
67 | NI00074095 | Gask,Octogonal,AlloySteel 5Cr,150mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 16 | 16 | 16 | 16 | Test sample
68 | NI00074096 | Gask,Octogonal,AlloySteel 5Cr,250mm NB,1500# for Ring type flange as per 16,5,as per ANSI B 16.20 | number | 3 | 3 | 3 | 3 | AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | NIL | NIL | Not Applicable
2 | QAP/ITP/QCP | NIL | IGP/ITP/DRTJ000870-21-22 Rev 02 Dt 23.02.2023 | Approved by TUV
3 | Drawing(s) | NA | NA | NA
4 | Procedure(s) | NIL | NIL | NA
5 | Datasheet(s) | NIL | NIL | NA
6 | Others (Specify) | PMI Spec: 6-81-0001 | NIL | NA

## Stages Witnessed
Stages Witnessed
QAP SL No.C.1 Visual check carriedout for on random selected 10% of Gaskets as per approved QAP -Found no injuries defects observed
QAP SL No. C.2 Witnessed Dimensional check and surface finish on random selected 10 % of gaskets from offered lot -Found with in acceptable tollerece llimites
QAP SL NO C.3 Witnessed hardness test on random selected 10% of gaskets from offered lot-Found meeting the requirement
QAP SL NO. C.4 Witnessed PMI test random selected 10% of gaskets from offered lot as per material specification-Found acceptable and reports attetested for records,
QAP SL No C.5 Verfied Marking( Month /Year/Mfr Name.Ring No,Grade, Heat No as per B16.20 on random seleceted gasket -Found inorder
QAP SL No. 3 Witnessed Zinc white Electro plating Thickness measurement -Found with in acceptable limits

## Document reviewed
Document reviewed
QAP SL NO A.1 Reviewed Raw material Lab test certificates as per material specification -Found acceptable and attetsed for records,.
QAP Note No 1. Reviewed F5 material heat treatment chart -Found acceptable
QAP SL No.D1 Reviwed manufacturer Test certificate as per EN 10204 3.1 for all offered Soft iron and F5 gaskets -Found inorder
Verified Calibration Status of testing instrument used for inspection - Found Valid.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | veriner Caliper | 0-300 mm | 0035993 | 02.01.2024 | JRPM-CCTR-DIM-2023-0081 | Yes |  | Yes
2 | Vernier caliper | 0-600 mm | 0059375 | 02.07.2023 | JRPM-CCTR-DIM-2023-0051 | yes |  | No
| Measuring tape | 0-15 mtr | PE-U2-MT-010 | 18.05.2023 | TII221119-8-3 | yes
| Hardness tester | 336 HBW | 12051 | 15.06.2023 | SSMS/HRDT/0146 |  | Yes
3 | Hardness tester | 225HBW | 308/25 | 02.01.2024 | JRPM-CCTR-DIM-2023-0026 | Yes
4 | surface roughness tester | 0-360 Micro meter | 301280903 | 02.01.2024 | JRPM-CCTR-DIM-2023-0048 | Yes
5 | PMI machine | Niton XL 800 | 74307 | 17.011.2023 | Tii/CAL/IGP/11379 | Yes
Type equation here.
"Type equation here."

## Areas of concerns
Areas Of Concern
Nil

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: