## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 010101000720/53
SAP number | 8116951219
Notification Number | Email dtd 03.08.2021
Project Name & Location | 3900-CES-INP
Client Name | RELIANCE INDUSTRIES LTD.
End User Name | RELIANCE INDUSTRIES LTD.
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | HEM INDUSTRIES
PO Number (Client PO on Vendor) | MMH/240278899 Dated 24/01/2020
Sub Vendor
PO Number (Vendor PO on Sub Vendor)
Inspection Location | Plot No:262 – 1 & 2. Nr. 66Kva sub station,Demni Road,Dadra 396193Silvassa, UT of Dadra & Nagar
Inspection Date(s) | 04.08.2021

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
| 2000044034 | BLT HEX A193-B8M A194-8M MC 40MM M10Mat: SS316 Basic Value 28.00 INR/ EA 1,176.00 Mat spec, bolting: ASTM A193 GRADE B8M IGST 18.00 % 211.68 Mat spec, nut(s): ASTM A194 GRADE 8M Dimensional spec: ASME B18.2.1 Finish, bearing face: FINISHED Type, thread: METRIC COARSE Length, under head mm 40 Add reqrmts: WITH NUT Size: M10 | each | 42 | 0 | 0 | 0 | number
| 2000261928 | STDBLT+N B8 8 MC M20 140MMMat spec, stud bolt(s): ASTM A193 GRADE B8 Mat spec, nut(s): ASTM A194 GRADE 8 Design spec, stud bolt: ASME B1.1 Design spec, nut: ASME B18.2.2 Thread class symbol, stud bolt 2A Thread class symbol, nut: 2B Type, thread: METRIC COARSE Number, nuts per stud bolt: 2 Type, nut: HEXAGONAL Size: M20 Length: 140MM | each | 18 | 18 | 18 | 18 | meter
| 2000044034 | BLT HEX A193-B8M A194-8M MC 40MM M10Mat: SS316 Basic Value 28.00 INR/ EA 2,576.00 Mat spec, bolting: ASTM A193 GRADE B8M IGST 18.00 % 463.68 Mat spec, nut(s): ASTM A194 GRADE 8M Dimensional spec: ASME B18.2.1 Finish, bearing face: FINISHED Type, thread: METRIC COARSE Length, under head mm 40 Add reqrmts: WITH NUT Size: M10 | each | 92 | 0 | 0 | 0 | km
| 2000044034 | BLT HEX A193-B8M A194-8M MC 40MM M10Mat: SS316 Mat spec, bolting: ASTM A193 GRADE B8M Mat spec, nut(s): ASTM A194 GRADE 8M Dimensional spec: ASME B18.2.1 Finish, bearing face: FINISHED Type, thread: METRIC COARSE Length, under head Add reqrmts: WITH NUT Size: M10 | each | 59 | 0 | 0 | 0 | meter (number)
| 2000058852 | BLT HEX A193-B8M A194-8M MC 50MM M10Mat: SS316 Mat spec, bolting: ASTM A193 GRADE B8M Mat spec, nut(s): ASTM A194 GRADE 8M Dimensional spec: ASME B18.2.1 Type, thread: METRIC COARSE Length, under head Add reqrmts: WITH NUT Size: M10 .ASTM A 193M GRADE B8-1994B OR BS970-1991##BOLT WITH 2MM HOLE FOR LOCK WIRE IN HEAD | each | 20 | 0 | 0 | 0 | km (number)
| 2000221110 | BLT HEX B8M GR 8M MC 70MM M10 Mat: SS316 Mat spec, bolting: ASTM A193M GRADE B8M CLASS 1 Mat spec, nut(s): ASTM A194M GRADE 8M Dimensional spec: ASME B18.2.1 Type, thread: METRIC COARSE Length, under head mm 70 Add reqrmts: WITH NUT & WASHER Size: M10 | each | 83 | 0 | 0 | 0 | each
| 2000547789 | BLT HEX B8M GR 8M MC 75MM M10 Mat: SS316 Mat spec, bolting: ASTM A193 GRADE B8M Mat spec, nut(s): ASTM A194M GRADE 8M Dimensional spec: IS 1364 Type, thread: METRIC COARSE Tolerances, thread, bolt: IS:4218 Length, under head mm 75 Add reqrmts: FULL THREAD Add reqrmts: WITH HEX NUT | each | 3 | 0 | 0 | 0 | Piece
| 2001877449 | BLT HEX UNS S32205 UNSS32205 MC 50MM M10Mat spec, bolting: UNS S32205 Mat spec, nut(s): UNS S32205 Finish, bearing face: --- Type, thread: METRIC COURSE Length, under head mm 50 Length, thread mm 50 Size: M10 BLT HEX UNSS32205 M10 50MM | each | 4 | 4 | 4 | 4 | Test sample
| 2001888318 | BLT HEX 2205 2205 MC 40MM M10Mat spec, bolting: DUPLEX 2205 Mat spec, nut(s): DUPLEX 2205 Finish, bearing face: --- Type, thread: METRIC COURSE Length, under head Add reqrmts: WITH HOLE Length, thread Size: M10SIZE:M10X40MM## REQUIREMENT:BOLT END SIDE WITH HOLE | each | 50 | 50 | 50 | 50 | AU - All Unit
| 2001888319 | BLT HEX 2205 2205 MC 60MM M10Mat spec, bolting: DUPLEX 2205 Mat spec, nut(s): DUPLEX 2205 Finish, bearing face: --- Type, thread: METRIC COURSE Length, under head Add reqrmts: WITH HOLE Length, thread Size: M10 SIZE:M10X60MM##REQUIREMENT:BOLT END SIDE WITH HOLE | each | 40 | 40 | 40 | 40 | lot
| 2000455427 | BLT HEX B8 8 MC 40MM M6Mat: SS304Mat spec, bolting: ASTM A193M GRADE B8Mat spec, nut(s): ASTM A194 GRADE 8 Dimensional spec: ASME B18.2.1 Finish, bearing face: FINISHED Type, thread: METRIC COARSE Length, under head mm 40 Add reqrmts: WITH NUT Length, thread mm 40 Size: M6 | each | 50 | 0 | 0 | 0 | Set
| 2002134281 | STDBLT+N B8 8 MC M10 75MMMat spec, stud bolt(s): ASTM A193 GRADE B8Mat spec, nut(s): ASTM A194 GRADE 8Design spec, stud bolt: ASME B18.2.2 Design spec, nut: ASME B1.1 Thread class symbol, stud bolt 2A Thread class symbol, nut: 2B Type, thread: METRIC COARSE Number, nuts per stud bolt: 2 Type, nut: HEX Add reqrmts: WITH WASHER Size: M10 Length: 75 | each | 26 | 26 | 26 | 26 | Running Meter
| 2000336767 | BLT HEX A193-B8M A194-8M MC 45MM M10Mat: SS316 Mat spec, bolting: ASTM A193 GRADE B8M Mat spec, nut(s): ASTM A194 GRADE 8M Dimensional spec: ASME B18.2.1 Type, thread: METRIC COARSE Length, under head mm 45 Add reqrmts: WITH NUT AND WASHER Size: M10 | each | 17 | 0 | 0 | 0 | kg
| 2000640753 | BLT HEX B8M GR 8M MC 35MM M10 Mat: SS316L Mat spec, bolting: ASTM A193M GRADE B8M CLASS 1 Mat spec, nut(s): ASTM A194M GRADE 8M Dimensional spec: IS 1364 Type, thread: METRIC COARSE Tolerances, thread, bolt: IS:4218 Length, under head mm 35 Add reqrmts: FULL THREADED Add reqrmts: WITH HEX NUT Size: M10 | each | 23 | 0 | 0 | 0 | metric ton (tonne)
| 2001014298 | WASHER,PLAIN;SIZE:M10;MOC:SS316Drawing & Item Number: 5437-2001/44 | each | 43 | 43 | 43 | 43 | ton
| 2001450198 | STDBLT+N B8 8 MC M10 65MMMat spec, stud bolt(s): ASTM A193 GRADE B8 Mat spec, nut(s): ASTM A194 GRADE 8 Design spec, stud bolt: ASME B1.1 Design spec, nut: ASME B18.2.2 Thread class symbol, stud bolt 2A Thread class symbol, nut: 2B Type, thread: METRIC COARSE Number, nuts per stud bolt: 2 Type, nut: HEXAGONAL Size: M10 Length: 65MM Drawing & Item Number: VCPVC-3-526/2A,4A | each | 14 | 14 | 14 | 14 | cubic millimetre
| 2000278841 | WASH GEN CS SPRING -- -- -- M10 Mat: CARBON STEEL Mat, spec: IS 4072 Type: SPRING Size: M10 AS PER IS 4072:1975 | each | 50 | 50 | 50 | 50 | cubic centimeter
| 2000330263 | BLT HEX B8M GR 8M MC 100MM M10Mat: SS316L Mat spec, bolting: ASTM A193M GRADE B8M CLASS 1 Mat spec, nut(s): ASTM A194M GRADE 8M Dimensional spec: ASME B18.2.1 Type, thread: METRIC COARSE Length, under head Add reqrmts: WITH TWO NUTS AND WASHER Length, thread Size: M10 | each | 50 | 0 | 0 | 0 | cubic meter
| 2000064220 | BLT HEX A193-B8M A194M-2H MC 50MM M20Mat: SS304 Mat spec, bolting: ASTM A193M GRADE B8 Mat spec, nut(s): ASTM A194M GRADE 2H Dimensional spec: ASME B18.2.1 Type, thread: METRIC COARSE Length, under head mm 50 Add reqrmts: WITH NUT Size: M20 | each | 25 | 0 | 0 | 0 | cubic inch
| 2000044040 | BLT HEX SS304 A194M MC 25MM M6Mat: SS 304Mat spec, bolting: ASTM A193M GRADE B8 18.00 Mat spec, nut(s): ASTM A194M GRADE 2H Dimensional spec: ASME B18.2.1 Pitch, thread coarse: 1.0MM Type, thread: METRIC COARSE Length, under head mm 25 Add reqrmts: WITH NUT Length, thread mm 25 Size: M6 | each | 100 | 0 | 0 | 0 | cubic foot
| 2000214938 | WASH GEN CS SPRING -- -- -- M8 Mat: CARBON STEEL Mat, spec: ASTM A515M Dimensions, spec: ASME B18.2.1 Type: SPRING Size: M8 ISSA Code: 6952- AS PER A515-1992 | each | 500 | 500 | 500 | 500 | mm
| 2000218203 | WASH GEN SS304 PLAIN 6.5MM 12MM 1MM M6Mat: STAINLESS STEEL Dimensions, spec: ASME B18.2.1 Type: PLAIN Diameter, id: 6.5MM Diameter, od: 12MM Thickness: 1MM Size: M6 | each | 500 | 500 | 500 | 500 | cm
| 2000218204 | WASH GEN SS304 PLAIN 8MM 18MM 1.1MM M8 Mat: STAINLESS STEEL Dimensions, spec: ASME B18.2.1 Type: PLAIN Diameter, id: 8 Diameter, od: 18 Thickness: 1.1 Size: M8 | each | 500 | 0 | 0 | 0 | in
| 2000218206 | WASH GEN SS304 PLAIN 10.8MM 22MM 1.6MMMat: STAINLESS STEEL Dimensions, spec: ASME B18.2.1 Type: PLAIN Diameter, id: 10.8 Diameter, od: 22 Thickness: 1.6 Size: M10 | each | 500 | 0 | 0 | 0 | foot
| 2000547806 | BLT HEX B8 GR 8M MC 30MM M8Mat spec, bolting: ASTM A193M GRADE B8 Mat spec, nut(s): ASTM A194M GRADE 8M Dimensional spec: ASME B18.2.1 Type, thread: METRIC COARSE Length, under head Size: M8 | each | 200 | 0 | 0 | 0 | mile
| 2001520959 | SCREW HEX SCK ALN A193-B8 MC 50MM M10 Mat: STAINLESS STEEL 304 Type: SOCKET HEAD CAP SCREW Mat, spec: ASTM A193 GRADE B8 Type, thread: METRIC COARSE Length, thread mm 50 Length, under head mm 50 Size, socket mm 8 Size: M10 | each | 100 | 100 | 100 | 100 | yard
| 2000390826 | SCREW HEX SCK ALN BOLT 12.9 MC 60MM M12Mat: HIGH TENSILE ALLOY STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: ISO 898/1 CLASS 12.9 Hardness: HRC 39-44 Type, thread: METRIC COARSE Length, thread mm 35MM Length, under head mm 60 MM Size, socket mm 10MM Size: M12 | each | 2 | 2 | 2 | 2 | liter
| 2000390826 | SCREW HEX SCK ALN BOLT 12.9 MC 60MM M12Mat: HIGH TENSILE ALLOY STEEL Type: SOCKET HEAD CAP SCREW Mat, spec: ISO 898/1 CLASS 12.9 Hardness: HRC 39-44 Type, thread: METRIC COARSE Length, thread mm 35MM Length, under head mm 60 MM Size, socket mm 10MM Size: M12 | each | 13 | 13 | 13 | 13 | kl
| 2001016877 | WASH GEN SS304L PLAIN 11MM 32MM 2MMMat: STAINLESS STEEL Mat, spec: ASTM A240 TYPE 304L Type: PLAIN Diameter, id: 11 Diameter, od: 32MM Thickness: 2 Size: M10 | each | 110 | 110 | 110 | 110 | cl
| 2001753455 | NUT MTR A194-8M HEX MC M16Mat: SS304 Mat, spec: ASTM A194 GRADE 8M Type: HEXAGONAL Type, thread: METRIC COARSE Size: M16 | each | 70 | 0 | 0 | 0 | ml
| 2001877435 | UT MTR UNS S32205 HEX MC M10Mat: ALLOY STEEL Mat, spec: UNS S32205 Type: HEXAGONAL Type, thread: METRIC COARSE Size: M10 NUT MTR UNS S32205 HEX MC M10 | each | 28 | 28 | 28 | 28 | g
| 2001015520 | WASH GEN SS316L PLAIN 17MM 32MM 3.5MMMat: STAINLESS STEEL Mat, spec: ASTM A240 TYPE 316L Profile: ROUND Type: PLAIN Diameter, id: 17MM Diameter, od: 32MM Thickness: 3.5 Size: M16 | each | 800 | 0 | 0 | 0 | lb
| 2001877585 | NUT MTR UNS S32205 HEX MC M20Mat: ALLOY STEEL Mat, spec: UNS S32205 Type: HEXAGONAL Type, thread: METRIC COARSE Size: M20 NUT MTR UNS S32205 HEX MC M20 | each | 15 | 15 | 15 | 15 | oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM
2 | QAP/ITP/QCP | ITEMS: STUDS/BOLTS & NUTS REV.'0' DATE: 10.04.2009 ASTM A 193,ASTM A 194 |  | APPROVED BY RIL
3 | Drawing(s)
4 | Procedure(s)
5 | Datasheet(s)
6 | Others (Specify)

## Stages Witnessed
Stages Witnessed
QAP Sr No: 4 Sample selection carried out for Mechanical Test.
QAP Sr No: 6 Visual check on 10% randomly selected samples from each item- No injurious defects was Found at time of Inspection.
QAP Sr No: 6 Threads checked with GO & NOGO gauge on 10% quantity from all item – Found satisfactory
QAP Sr No: 6 Dimension check on 10% randomly selected samples from each item-Found within tolarance
QAP Sr No: 6 Marking verified on 10% randomly fasteners from total offered quantity Found to meet specification requirement
QAP Sr No:7 PMI check on 10% randomly selected samples from each item as per approved QAP – Found to meet specification requirements
QAP Sr No:7 Hardness check on 10% randomly selected samples from each item as per approved QAP – Found to meet specification requirements

## Document reviewed
Document reviewed
QAP Sr NO:1 & 5 MTC & Lab Check Test Certificate of Raw Material For Mechanical test ( Tensile Test / Hardness Test / Proof Load Test) As Applicable & Chemical Analysis reviewed- Found in Order
QAP Sr NO:8 Final MTC NO: HI/751,752,753,754,755,756,757,758,759,760/202122 of Fasteners Reviewed -Found in order

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
| Vernier Caliper | 0-300 mm | 180811100 | 01.12.2021 | NCQC¬M/021220/60 Dt.: 02.12.2020 | Yes |  | Yes
No

## Areas of concerns
Areas Of Concern
nil

## Pending Activities
Pending Activities from this visit
nil

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: