## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number | 8116951217
Notification Number | Email Dated 12.03.2022
Project Name & Location | JMD-DTA-REV-PCG
Client Name | M/s. Reliance Industries Limited
End User Name | M/s. Reliance Industries Limited
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name | M/s. HEM ENGINEERING CORPORATION, Tarapur
PO Number (Client PO on Vendor) | 252/240425471 Dated 25/01/2022
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Boisar
Inspection Date(s) | 16.03.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 2001915378 | GSKT SW GRP 316 AL800 AL800 CL600 3" SPWD WITH AL800 INNER RING & 316 OUTER RING, ASME B 16.20 | each | 70 | 70 | 70 | 70 | number
2 | 2001778356 | GSKT SW GRP AL800 AL800 AL800 CL600 24" SPWD WITH AL800 INNER RING & OUTER RING, ASME B 16.20 | each | 50 | 50 | 50 | 50 | meter
3 | 2002041794 | GSKT SW GRPH AL800 AL800 AL800 CL600 6" SPWD WITH AL800 INNER RING & OUTER RING, ASME B 16.20 | each | 100 | 100 | 100 | 100 | km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | E&M-STATIC-PS/IR-022 R02 | NA | RIL Document
2 | QAP/ITP/QCP | RIL/Mech/QAP/03 R00 | QAP No 5555/01 R00 | Approved by RIL
3 | Drawing(s) | NA | NA | NA
4 | Procedure(s) | NA | NA | NA
5 | Datasheet(s) | NA | NA | NA
6 | Others (Specify) | 10080-1-SS-PP-004 Part - VI Rev-1, 10080-1-SS-PP-005, 10080-1-SS-PP- 018 | NA | RIL Document

## Stages Witnessed
Stages Witnessed
QAP CL NO 3.1: Visual inspection carried out for randomly selected 10% qty for each line item for surface finish & workmanship. No significant surface defect observed at time of inspection. Found acceptable.
QAP CL NO 3.1: Dimensional & fitment inspection witnessed for randomly selected 10% qty for each line item as per QAP requirement. Dimensions found as per specification & PO. Found acceptable.
QAP CL NO 3.2: Seal ability, compressibility, recovery test & Performance test witnessed for 1% qty on prototype gasket as per QAP for standard Gaskets - found satisfactory.
QAP CL NO 3.3: PMI witness for 10% qty at random for each line of item as per specification:- found to meet the requirements.
QAP CL NO 3.4: Marking & Colour coding verified for 10% qty at random from offered lot as per QAP, Found acceptable.
QAP CL NO 3.5: Packing and preservation of Offered Gasket randomly verified as per CL.10 of PSIR-022 _latest revision -Found satisfactory
QAP CL NO 2.2: Reviewed Radiography Films of 24" Gasket Out Ring Long Seam Weld as per ASME Sec VIII Div 1, UW-51- found satisfactory.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP CL no 1.1: Raw material TC (Winding, Inner Ring & Outer Ring) reviewed as per Material Specification. Found in order.
QAP CL no 1.2: Raw material TC (Filler Material-Graphite) reviewed as per Material Specification. Found in order.
QAP CL no 1.3: Reviewed PMI report of Raw Material as per specification - found in order
QAP CL no 3.6: Reviewed Manufacturer's provide MTC (EN 10204 Type 3.2- TC No: 5442/A Dated 27.10.2021) as per QAP & PO- found in order.
QAP CL no 2.3: Reviewed PT Report of 24" Gasket Out Ring Long Seam Weld as per ASME Sec VIII Div 1, Appendix 8- found satisfactory.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Measuring Tape | 0-5000 mm | HEC/TAPE/36 | 14.09.2022 | 2021-22/CC/IDS/775 Dated 17/09/2021 | Yes |  | Yes
2 | Vernier Caliper | 0-300 mm | HEC/VC/62 | 22.08.2022 | 2021-22/CC/IDS/658 Dated 24/08/2021 | Yes |  | No
3 | Portable Gas Detector | 0-5000 ppm | 19310001 | 02.12.2022 | 099/21 Dated 03/12/2021 |  | Yes
4 | Pressure Gauge | 0-42 kg/cm2 | PG-10 | 28.08.2022 | 21080232 Dated 29.08.2021 | Yes
5 | Pressure Gauge | 0-70 kg/cm2 | PG-30 | 29.01.2023 | 22010226 Dated 30.01.2022 | Yes
6 | Gauge for Load in Ton | 0-160 Tons | AI/2747/13 | 17.09.2022 | AI/TC-14485/2-22 Dated 18.09.2021 | Yes
7 | PMI Machine XLt898 | --- | 11611 | 23.09.2022 | HAS/32/21 Dated 24/09/2021 |  | Yes

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
None
Identification of Inspected Item(s):
10% Witnessed gasket identified with double soft stamp on sticker & rest single on mfg tag as “ “ for Identification.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable.
IRN can be issued for PO Item numbers:
All
Expenses:
Remarks: