## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number
Project Name & Location | Naya Nangal Unit, Punjab
Client Name | M/s Zed Valves Company Private Limited
End User Name | M/s National Fertilizers Limited
DEC / PMC / EPC Name | Not applicable
DEC / PMC / EPC Number | Not applicable
Vendor Name | M/s Zed Valves Company Pvt Ltd.
PO Number (Client PO on Vendor) | PN/SP/2020/57/1/6121 Dated 25.06.2021
Sub Vendor | Not applicable
PO Number (Vendor PO on Sub Vendor) | Not applicable
Inspection Location | Zed Valves Company Pvt Ltd, 123/8, Opp Pushpak Estate, Rakhial, Ahmedabad - 380023.
Inspection Date(s) | 22.09.2021

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 4307766 | Globe Valve Size: 32 NB X ND40 Class, FE MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-32-8247 to ZV-32-8261 Witnessed Valve Sr. No:- ZV-32-8250 & ZV-32-8256 | Piece | 15 | 15 | 15 | 15 | number
2 | 4307073 | Globe Valve Size: 40 NB X ND40 Class, FE MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-40-8262 to ZV-40-8276 Witnessed Valve Sr. No:- ZV-40-8266 & ZV-40-8275 | Piece | 15 | 15 | 15 | 15 | meter
3 | 4307074 | Globe Valve Size: 50 NB X ND40 Class, FE MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-50-8277 to ZV-50-8291 Witnessed Valve Sr. No:- ZV-50-8277 & ZV-50-8288 | Piece | 15 | 15 | 15 | 15 | km
4 | 4307076 | Globe Valve Size: 65 NB X ND40 Class, FE MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-65-8292 to ZV-65-8297 Witnessed Valve Sr. No:- ZV-65-8295 | Piece | 6 | 6 | 6 | 6 | meter (number)
5 | 4307077 | Globe Valve Size: 80 NB X ND40 Class, FE MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-80-8298 to ZV-80-8303 Witnessed Valve Sr. No:- ZV-80-8300 | Piece | 6 | 6 | 6 | 6 | km (number)
6 | 4307058 | Globe Valve Size: 100 NB X ND40 Class, FE MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-100-8304 to ZV-100-8309 Witnessed Valve Sr. No:- ZV-100-8307 | Piece | 6 | 6 | 6 | 6 | each
7 | 4307082 | Globe Valve Size: 32 NB X ND40 Class, BW MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-32-8310 to ZV-32-8329 Witnessed Valve Sr. No:- ZV-32-8311 & ZV-32-8320 | Piece | 20 | 20 | 20 | 20 | Piece
8 | 4307083 | Globe Valve Size: 40 NB X ND40 Class, BW MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-40-8330 to ZV-40-8349 Witnessed Valve Sr. No:- ZV-40-8333 & ZV-40-8340 | Piece | 20 | 20 | 20 | 20 | Test sample
9 | 4307084 | Globe Valve Size: 50 NB X ND40 Class, BW MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-50-8350 to ZV-50-8369 Witnessed Valve Sr. No:- ZV-50-8355 & ZV-50-8360 | Piece | 20 | 20 | 20 | 20 | AU - All Unit
10 | 4307086 | Globe Valve Size: 65 NB X ND40 Class, BW MOC: ASTM A 216 Gr. WCB, IBR Manufacturer Valve Sr No. ZV-65-8370 to ZV-65-8379 Witnessed Valve Sr. No:- ZV-65-8375 | Piece | 10 | 10 | 10 | 10 | lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | Not Applicable | ZVPL/OA 1213/21-22/01 Rev-0 | Approved by NFL
3 | Drawing(s) | Not Applicable | ZV/GBV/ND-40/32TO100/01, Rev-0 ZV/GBV/ND-40/32TO65/02 | Approved by NFL
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
QAP Clause 3.1: Witnessed Hydro test of Body, Seat & Backseat for Globe Valves for 10% Qty of offered valves as per approved drawing - No Pressure drop or leakage observed during holding time, hence found satisfactory.
QAP Clause 3.2: Witnessed Pneumatic (Air) test of Seat for Globe Valves for randomly selected 10% Qty of offered valves as per approved drawing - No Pressure drop or leakage observed during holding time, hence found satisfactory.
QAP Clause 3.3 Dimensions checked of 10% randomly selected quantity of Globe Valves for each PO line items as per approved QAP & approved drawing– Observed dimensions found within tolerance limits.
Visual inspection carried out of 100% qty of Globe Valves at inside and outside as accessible surface area - No injurious surface defects, surface imperfections or mechanical damages were observed, Hence found satisfactory.
All measuring instruments/ equipments were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Stage No. 1.1: Reviewed Material test certificates as declared by supplier for Body, Bonnet as per approved drawing, QAP & relevant specification - Found to meet material specification requirements
QAP Stage No. 1.2: Reviewed Material test certificates as declared by supplier for Stem, Body Seat Ring, Disc, as per approved drawing, QAP & relevant specification - Found to meet material specification requirements.
QAP Stage No. 1.3: Reviewed Material test certificates as declared by supplier for stud/nuts (Body/Bonnet Joints) as per approved drawing, QAP & relevant specification - Found to meet material specification requirements
Reviewed calibration certificates of measuring instruments & pressure gauges along with master gauge certificates as used for calibration of pressure gauges - Found in order to have valid calibration for intended use.
Reviewed Manufacturer Final Test Certificates of valves as per EN 10204 (Type 3.1) No.: 1213-01, 1213-02, 1213-03, 1213-04, 1213-05, 1213-06, 1213-07, 1213-08, 1213-09 & 1213-10 Dtd. 21.09.2021 - Found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Pressure Gauge | 0-70 Kg/Cm² | PG-03 | 20.11.2021 | CC312621000007277F | Yes |  | Yes
2 | Pressure Gauge | 0-28 Kg/Cm² | PG-09 | 20.11.2021 | CC312621000007283F | Yes |  | No
3 | Vernier Caliper | 0-300 mm | VC-01 | 10.09.2022 | NCQC-M/110921/27 | Yes
4 | Vernier Caliper | 0-600 mm | VC-08 | 25.08.2022 | ZVCPL/0821/002 | Yes

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit
None

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: