## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number
Project Name & Location | PRAJ IND
Client Name | PRAJ IND
End User Name
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | MAXGEAR
PO Number (Client PO on Vendor)
Sub Vendor
PO Number (Vendor PO on Sub Vendor)
Inspection Location | MIDC KUPAWAD
Inspection Date(s) | 6-7.10.2023

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
. | . | PRAJ IND. LTD.' P.O. on MAX-GEARS PVT. LTD. -P.O. Number :4520197942 Date :19.07.2023 | [5 empty] | number
20 | 5214595 | GEAR-BOX-ASSLY-FOR-DRYER-1140-M2 Tag No : G-1801 | each | 2 | 1 | 1 | 1 | meter
. | . | PRAJ IND. LTD.' P.O. on MAX-GEARS PVT. LTD. - P.O. Number :4500100421 Date :15.03.2023 | [5 empty] | km
10 | 5213441 | DRIVE-GEAR-PINION-ASSLY-DRYER-1650-M2 | each | 1 | 1 | 1 | 1 | meter (number)
. | . | [6 empty] | km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM
2 | QAP/ITP/QCP |  | QAP for Dryer Gearbox Assembly Document Number : MG/PIL/DGB/QAP/22-23/009 Revision Number : 001 QAP for Dryer Open Pinion Assembly Document Number : MG/PIL/DGB/QAP/22-23/006 Revision Number : 001 | PRAJ approved with comments
3 | Drawing(s) |  | MAIN G. A. DRAWING-269.002.H-3-400-1.00-(OGP)[502.042.400.00] REV.00 BASE FRAME DRG-502.042.400.04 REV.00 CANOPY FOR PINION & GEAR - 269.002.H-3-500.06A-R1 (OGP) Rev.1 MAIN G. A. DRAWING-269.002.H-3-500.00-(OGP) [269.002.H-3-500 OGP-00] REV.00 OPEN GEAR PINION-269.002.H-3-500.02-(OGP)[269.002.H-3-500.02A (OGP)] REV.00 OPEN GEAR WHEEL-269.002.H-3-500.01-(OGP)[269.002.H-3-500.01A (OGP)] REV.00 STOOL MACHINING DRAWING - 269.002.H-3-500.05A (OGP) REV.00 | PRAJ approved code-D PRAJ approved code-A PRAJ approved . PRAJ approved code-D PRAJ approved code-D PRAJ approved code-D PRAJ approved code-D
4 | Procedure(s)
5 | Datasheet(s)
6 | Others (Specify)

## Stages Witnessed
Stages Witnessed
PRAJ IND. LTD.'s P.O. on MAX-GEARS PVT. LTD. -P.O. Number :4520197942 Date :19.07.2023 PO SR.NO-020 /GEAR-BOX-ASSLY-FOR-DRYER-1140-M2 ,Tag No : G-1801
cl-7- Final Assembly Dimensional Inspection:- Major dimensions verified & for GB & base frame observed within limit in ref with approved drawings.
cl-8- Trial Run at No Load condition for 4hrs:- The trial run witnessed at no load condition for 4hrs duration. During the test -Leakage Inspection visually checked & no leakgae or seepage observed. The parameters viz. RPM, Noise Level, Vibration Level, Temperature of bearings checked and observed within limt. Identification verified and found in order.
cl-9- Visual Inspection of assembled Gear box- Overall visual insepction carried out & found satisfactory.
PRAJ IND. LTD.' P.O. on MAX-GEARS PVT. LTD. - P.O. Number :4500100421 Date :15.03.2023 PO SR.NO-010/DRIVE-GEAR-PINION-ASSLY-DRYER-1650-M2
QAP CL-4 - Finish Canopy's Dimensional Inspection Major dimensions verified and found in order as per approved drawing. Overall visual inspection carried out and found satisfactory.
QAP CL-7 - Finish Stool Dimensional Inspection Major dimensions verified and found in order as per approved drawing.
QAP CL-8 - Visual Inspection of Stool Overall visual inspection carried out and found satisfactory.
QAP CL-9 - Finish open Gear Pinion Dimensional Inspection Major accesible dimensions verified( since the shaft / pinion were assembled) and found in order as per approved drawing.
QAP CL-10 - Visual Inspection of open Gear Pinion Overall visual inspection carried out and found satisfactory.
QAP CL-11 - Finish open Gear Wheel Dimensional Inspection Major dimensions verified and found in order as per approved drawing.
QAP CL-12 - Visual Inspection of open Gear Wheel Overall visual inspection carried out and found satisfactory.
Identification verified and found in order.
Vendor offered the Pinion gear /shaft assembly duly mounted on the stools.

## Document reviewed
Document reviewed
PRAJ IND. LTD.'s P.O. on MAX-GEARS PVT. LTD. -P.O. Number :4520197942 Date :19.07.2023 PO SR.NO-020 /GEAR-BOX-ASSLY-FOR-DRYER-1140-M2 ,Tag No : G-1801
QAP CL-2-Pre-fabrication Casing's raw material Inspection MTCs /MTR reviewed & found in order.
QAP CL-3-Fabricated Casing's Inspection Inspection report / Leak test report /D.P. Test report & S.R. Graph reviewed & found in order.
QAP CL-4 Finish Casing's Inspection Test report reviewed & found in order.
QAP CL-5 Internal's Raw Material- Material T.C. /manufacturers T.C./U.T. report -reviewed & found in order.
QAP CL-6 Finish Internal's Inspection Test report reviewed & found in order.
QAP CL- Final Assembly Dimensional Inspection:- Dimension report reviewed & found in order.
QAP CL-Trial Run at No Load condition for 4hrs:- Test run test report reviewed & found in order.
QAP CL-Visual Inspection of assembled Gear box- .Insp. report reviewed & found in order.
PRAJ IND. LTD.' P.O. on MAX-GEARS PVT. LTD. - P.O. Number :4500100421 Date :15.03.2023 PO SR.NO-010/DRIVE-GEAR-PINION-ASSLY-DRYER-1650-M2
QAP CL-2 & 3 - Canopy - Material TCs reviewed/ DPT report reviewed and found in order.
QAP CL-4 - Finish Canopy's Dimensional Inspection- dimension report reviewed and found in order.
QAP CL-5 - Pre-fabrication Stool raw material Inspection- Material TCs reviewed and found in order.
QAP CL-6 - Fabricated Stool Inspection-. Material TCs reviewed/DPT report reviewed/S.R. Graph reviewed and found in order.
QAP CL-7/8- Fabricated Stool Inspection- dimension/visual inspection report reviewed and found in order.
QAP CL-9/10- Finish open Gear Pinion -dimension/visual inspection report reviewed and found in order.
QAP CL-11/12- Finish open Gear Wheel -dimension/visual inspection report reviewed and found in order.
Calibrationt test reports reviewed and found in order.
MTR reviewed and found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Varnier caliper | 0-2000 mm | MG/VER/A/06 | 28.03.2024 | ACC/2023//03/3404 | Yes |  | Yes
2 | Measuring tape | 0-3 mtr | 9841 | 24.07.2024 | UQE/23G//292/01 | Yes |  | No
3 | Instruments used during the Gear box - Refer Mfg. status report |  |  |  |  | Yes | Yes

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Model, sr.no. hard punched on the pinion gear OD and gear wheel face by MAXGEAR. And on the housing for GB. TUV hard stamp punched as " " near the same.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable
IRN can be issued for PO Item numbers:
Expenses:
Remarks: