## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 331306223523
SAP number | 8121772855
Notification Number | Email Dated 16.08.2023
Project Name & Location
Client Name | Integral Coach Factory, Chennai
End User Name | Integral Coach Factory- Indian Railways, Chennai
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name | RESPONSIVE INDUSTRIES LTD
PO Number (Client PO on Vendor) | 07230171101654 dated 14-JUL-23
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Responsive Industries Ltd., Mahagaon Road, Betegaon Village, Boisar (East), Tal.Palghar, Dist. Palghar- 401501 Maharashtra.
Inspection Date(s) | 21.08.2023, 22.08.2023 & 24.08.2023

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
001 | 30416334 | 2MM THICK FLEXIBLE PVC FLOORING SHEET SIZE: 2 x 1620 x 16000 MM CONFORMING TO SPECN. RDSO/2006/CG-12 REV.01 WITH AMD.01 TO 03, COLOUR: RDSO APPROVED SAMPLE No. NACFLG-02. THE SCOPE OF SUPPLY SHALL COVER A LENGTH OF 20 METERS OF 3 MM DIA COLOUR PVC ELECTRODE PER ROLL OF 16000 MM LENGTH OF PVC SHEET. ELECTRODE COLOUR SHADE SHOULD MATCH THE RDSO APPROVED SAMPLE NO. NACFLG-02. Batch No: 23 | Set | 146 | 146 | 146 | 146 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | NA | NA | NA
2 | QAP/ITP/QCP | NA | NA | NA
3 | Drawing(s) | NA | NA | NA
4 | Procedure(s) | NA | NA | NA
5 | Datasheet(s) | NA | NA | NA
6 | Others (Specify) | Specification No.: RDSO/2006/CG-12 Rev.1 | NA | Indian Railways Document

## Stages Witnessed
Stages Witnessed
Visual inspection carried of Flexible Flooring PVC sheet of 13 nos roll from 146 nos as per specification for the smoothness, free from pinholes, blisters, porosity, blow holes, lamination and other visual defects.- Found satisfactory.
Witnessed Dimensional Inspection of Flexible Flooring PVC sheet of 13 nos roll from 146 nos for Length (16000 mm), Width (1620 mm) & thickness (2 mm) as per specification & PO, thickness observed 2.06 to 2.09 mm, length observed 16300 mm & Width observed 1629 mm- found satisfactory.
Witnessed Shade & Pattern of Flexible Flooring PVC sheet of 13 nos roll from 146 nos as per approved sample for Shade & Pattern (NACFLG-02)- found satisfactory.
Witnessed Tensile Strength at 1% elongation in the direction of manufacture and in the transverse direction from 2 nos roll (Roll No: 098290 & 098342), observed load more than 10 Kgf as per specification- found satisfactory.
Witnessed elongation break test, observed elongation more than required 150 mm minimum as per specification, found satisfactory.
Witnessed Chip Density on Top of Wear Layer as per speciifcation, observed between 100 to 160 nos- found satisfactory
Witnessed Tear Strength Flexible Flooring PVC, in the direction of manufacture and in the transverse direction, observed load more than required minimum 40 N/mm in the direction of manufacture & 50 N/mm in the transverse direction as per specification- found satisfactory.
Witnessed PVC weld strength test as per specification, observed breaking load more than minimum require 24 Kgf- found satisfactory.
Witnessed Residual Indentation of Flexible Flooring PVC as per specification, observed value less than 0.05 mm max- found satisfactory.
Witnessed Flexible Flooring PVC Shear Strength in Dry Condition with compreg & stainless steel as per specification, observed strength more tha 25 kg/6.25 sq. cm and Flexible Flooring PVC Shear Strength in Wet Condition with compreg & stainless steel as per specification, observed strength more tha 25 kg/6.25 sq. cm of compreg & more tahn 20 kg/6.25 sq. cm for stainless steel - found satisfactory.
Witnessed Identation Test of Flexible Flooring PVC at 27 degree celcius(+,- 2) after 1 minute & 10 minutes, observed value less than 0.65 mm max after 1 minute & 0.85 max after 10 minutes- found satisfactory.
Witnessed Identation Test of Flexible Flooring PVC at 46 degree celcius(+,- 2) after 30 seconds, observed value less than 1.05 mm max after 30 seconds- found satisfactory.
Witnessed Flexibility Test with 20 mm radius mandrel of Flexible Flooring PVC after condition at 0 dgree celsius for 1 hrs, no crack observed- found satisfactory.
Witnessed Heat Release Rate of Flexible Flooring PVC as per specification, observed Heat Release Rate less than required 69 Kw/m2 (max.) (R1HL3)- found satisfactory.
Witnessed Limiting Oxygen Index of Flexible Flooring PVC as per specification , observed Limiting Oxygen Index more than required 35 minimum- found satisfactory
Witnessed Wear Layer thickness of Flexible Flooring PVC as per specification, observed Wear Layer thickness more than required 1.1 mm (minimum)- found satisfactory.
Witnessed Homogeneity test of Flexible Flooring PVC as per specification - found satisfactory.
Witnessed Ply Adhesion Test of Flexible Flooring PVC as per specification, observed adhesion strength more than required 1.05 KN/M (minimum)- found satisfactory.
Witnessed Weight per meter square of Flexible Flooring PVC as per specification, observed less than required 3000 gm/m2 (max)- found satisfactory
Witnessed Resistance to Spread of Flame for Flexible Flooring PVC as per specification, observed above required Min Class A- found satisfactory.
Witnessed Abrassion Resistance (Volume Loss) of Flexible Flooring PVC as per specification, observed volume loss less than required 0.25 cc (max)- found satisfactory.
Witnessed Deterioration of Visibility due to smoke from Flexible Flooring PVC as per specification, observed above required Min Class A- found satisfactory.
Witnessed Toxicity from Flexible Flooring PVC as per specification, observed toxicity less than required 1- found satisfactory.
Witnessed Dimensional Stability of Flexible Flooring PVC after conditioned for 6 hrs at temperature of 80 degree celcius as per specification, observed deviation less than required 0.25% (max)- found satisfactory.
Witnessed Moisture Movement of Flexible Flooring PVC after contioned in water for 72 hrs, observed Moisture Movement less than required 0.4% (max)- found satisfactory.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
Reviewed Sound Absorption Type Test report as per specification - found in order.
Reviewed Slip Resistance Type Test report as per specification - found in order.
Reviewed Abrasion Loss of Thickness Type Test report as per specification - found in order.
Reviewed Colour Fastness to Day Light Type Test report as per specification - found in order.
Reviewed Heat ageing & Exudation Type Test report as per specification - found in order.
Reviewed Curling Type Test report as per specification - found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
--- | As pe Vendor Instruments Master Calibration List | [6 empty] | Yes
No

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
NA
Identification of Inspected Item(s):
13 set Dimensional Inspected double soft stamped & rest single as " " near marking on the tag for Identifciation.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: