## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 050106154921/2
SAP number | 8119254777/100
Notification Number | Mail Dt 03.12.2021
Project Name & Location | NA
Client Name | MANALI PETROCHEMICAL LIMITED(5780)
End User Name | MANALI PETROCHEMICAL LIMITED(5780)
DEC / PMC / EPC Name
DEC / PMC / EPC Number
Vendor Name | GULF ENGINEERS AND CONSTRUCTORSPVT LTD(187)
PO Number (Client PO on Vendor) | 6200003289 Dated 19.11,2020
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Ernavoor
Inspection Date(s)
EPC Contractor | None

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
12 | ---- | Globe Valve, Size : 4'' X 1500#, Material : ASTM A351 CF8M, Tag No : 051-HV-457, Serial No : 2210028-022-001 | number | 01 | 01 | Refer Pending Activities |  | number
13 | ---- | Globe Valve, Size : 8'' X 300#, Material : ASTM B367 C3, Tag No : 051-HV-715, Serial No : 2210028-023-001 | number | 01 | 01 | Refer Pending Activities |  | meter
27 | ---- | Butterfly Valve, Size : 30'' X 150#, Material : ASTM A216 WCB, Tag No : 051-PV-931AA, Serial No : 2210028-028-001 | number | 01 | 01 | Refer Pending Activities |  | km
30 | ---- | Butterfly Valve, Size : 30'' X 150#, Material : ASTM A216 WCB, Tag No : 051-PV-938A, Serial No : 2210028-029-001 | number | 01 | 01 | Refer Pending Activities |  | meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | IOCL : IPPP-6417-8551-DS-051-0035 (T.EN : MR-1541-0001D-B1002-2210028 Rev.04) | 2210028-ITP Rev.04 | Approved by T.EN In code.02. Still Toyo & IOCL approval pending
3 | Drawing(s) | IOCL : MR-1541-0001D-A3102-2210028-GAD (T.EN : MR-1541-0001D-A3102-2210028-GAD-Rev 3A) | 2210028 Rev.3A | Approved by T.EN In code.03
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | IOCL : IPPP-6417-8551-DS-051-0035 (T.EN : MR-1541-0001D-A101-2210028-Specification sheet Rev 4A) | MR-1541-0001D-A3101-2210028 Rev 4A | Approved by T.EN In code.03
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
ITP Sl. No.: 2.2 (C)- Witnessed PMI test on Trim Parts (Stem, disc, Plu head, shaft, seat and cage) for Tag No : 051-HV-457, 051-HV-715 & 051-PV-938A – Test results meets the material specification and drawing requirement.
ITP Sl. No.: 3.1 - Visual examination was carried out the offered Butterfly & Globe Control Valves for Tag No : 051-HV-457, 051-HV-715 & 051-PV-938A – No Surface defects were noticed.
ITP Sl.No.: 3.1 - Witnessed Hydrostatic Test, 10% randomly selected from offered lot (per size/rating/material) Pressure & Holding time as per standard carried out for the offered Butterfly & Globe Control Valves for Tag No : 051-HV-457 & 051-PV-938A - No Leakages or Pressure Drop were observed found satisfactory and reports attested for records.
ITP Sl.No.: 5.1 - Witnessed 10% randomly (per size/rating/material) - Pneumatic (Air) - Seat Leakage test, Packing gland and fittings leak test as per Procedure carried out for the offered Butterfly Control Valve Tag No : 051-PV-931AA - Found within allowable leakage rate.
ITP Sl.No.: 5.1 - Witnessed 10% randomly (per size/rating/material) - Functional test, following parameter check (Calibration check, Fail Action, Valve Travel, Positioner Calibration, Linearity, Hysteresis & Actuator Leakage Test) carried out for the offered Butterfly Control Valve with respect to approved datasheet Tag No : 051-PV-931AA – Found Satisfactory.
ITP Sl.No.: 5.1 - Witnessed 10% randomly (per size/rating/material) Visual & Dimensional inspection carried out for the offered Butterfly Control Valve as per approved Drawings Tag No : 051-PV-931AA – Found within acceptable limits.
ITP Sl.No.: 5.3 - Witnessed Final Paint DFT & Colour Shade carried out for the offered Butterfly Control Valve (Body) Tag No : 051-PV-931AA - Result with respect to painting procedure - Found acceptable.

## Document reviewed
Document reviewed
ITP Sl.No.: 2.1- Reviewed Photocopy of Manufacturer test certificate for Body & Bonnet – Chemical and Mechanical requirements Found to meets the material specification. Report Attested for records.
ITP Sl.No.: 2.1 - Reviewed MPT report for CS Body Castings – Found in Order. Report Attested for records.
ITP Sl.No.: 2.2 - Reviewed Photocopy of Manufacturer test certificate for Trim Components – Chemical and Mechanical requirements Found to meets the material specification. Report Attested for records.
Reviewed factory acceptance Test report and Valve Signature Test report for Butterfly Control Valve Tag No : 051-PV-931AA - Found in Order.
Reviewed Calibration certificate of Measuring Instruments and Testing Equipment used for inspection - Found Valid.
Reviewed Calibration certificate of Measuring Instruments and Testing Equipment used for inspection - Found Valid.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Pressure Gauge |  |  |  | Calibration certificate not yet received from NABL Lab |  |  | Yes
No
Type equation here.
"Type equation here."

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
ITP Approved by T.EN In code.02. Still Toyo & IOCL approval pending
Pressure Gauge Calibration certificate not yet received from NABL Lab.
Vendor to Offer all Witness/Review Stage to TUV India as per ITP.

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: