## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number | Email Dtd. 12.04.2023
Project Name & Location | Fabrication of Piping Spools at M/s. LARSEN & TOUBRO LIMITED(PIPING CENTRE)
Client Name | AEPCOM Fasteners Private Limited
End User Name | M/s INDIAN OIL CORPORATION LIMITED (IOCL)
DEC / PMC / EPC Name | THYSSENKRUPP INDUSTRIAL SOLUTIONS (INDIA) PVT LTD
DEC / PMC / EPC Number | Not applicable
Vendor Name | AEPCOM Fasteners Private Limited, V U Nagar
PO Number (Client PO on Vendor) | 06L000926 / RAHUL B TARDE 17Dec22 Dated 17/12/2022
Sub Vendor | Not applicable
PO Number (Vendor PO on Sub Vendor) | Not applicable
Inspection Location | PLOT No.: 704/6, PHASE – 4, G.I.D.C., INDUSTRIAL ESTATE, VITHAL UDYOGANAR – 388 121.VIA : ANAND
Inspection Date(s) | 12.04.2023

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
23 | 60074-H044 | JACK SCREW, SIZE: M16 X 150MM LG, Material SA 320 GR. L7 | number | 100 | 100 | 100 | 100 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | ARM No.: 060074982 (R0) | Not Applicable. | Issued by M/s. L&T
2 | QAP/ITP/QCP | L&T/SQPC/FASTENERS/001, REV.00, DTD: 25.05.2020 | Not Applicable. | Approved by M/s. L&T
3 | Drawing(s) | Not Applicable. | Not Applicable. | Not Applicable.
4 | Procedure(s) | Not Applicable. | Not Applicable. | Not Applicable.
5 | Datasheet(s) | Not Applicable. | Not Applicable. | Not Applicable.
6 | Others (Specify) | Not Applicable. | Not Applicable. | Not Applicable.

## Stages Witnessed
Stages Witnessed
QAP Sr. No.: 4.1 – Product Identification & sampling carried out for testing – Found to meet applicable code and specification requirements.
QAP Sr. No.: 4.3 – Product Tensile, Wedge Load & Impact @-101°C test witnessed at NABL accredited lab on representative samples Identified by TUV – Found to meet the specification requirements.
QAP Sr. No.: 4.3 – Hardness test witnessed at manufacturer’s in-house testing facility randomly selected samples from offered line item – Found to meet the specification requirements.
QAP Sr. No.: 4.4 – MPI test witnessed on 10% randomly selected samples from offered line item – No surface indication were observed.
QAP Sr. No.: 4.5 – Visual check on 20% randomly selected samples from offered line item – Found free of injurious defects.
QAP Sr. No.: 4.5 – Dimension check on 20% randomly selected samples from offered line item – Found to meet the specification requirements.
QAP Sr. No.: 4.6 – Threads checked by std. GO / NO GO gauge on 20% randomly selected samples from offered line item – Found satisfactory.
QAP Sr. No.: 4.7 – PMI check on 20% randomly selected samples from offered line item – Found to meet the specification requirements.
QAP Sr. No.: 4.9 – Rust preventive coating verified of offered line item – Found to meet the requirements.
QAP Sr. No.: 4.10 – Marking & Stamping verified on 20% randomly selected samples from offered line item – Found in order.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Sr. No.: 1.1 – NDE & Heat treatment procedures – Found to meet the code and specification requirements.
QAP Sr. No.: 2.1 – Raw material test certificates reviewed for its technical content only as declared by manufacturer and endorsed by M/s AEPCOM – Found to meet the material specification requirements.
QAP Sr. No.: 3.2 – Heat treatment chart – Found to meet the specification requirements.
QAP Sr. No.: 4.2 – Product Chemical lab test report – Found to meet the specification requirements.
QAP Sr. No.: 6.1 – Manufacturer’s Test Certificate No.: AEPCOM/TC/22, Dtd. 12.04.2023 – Found to meet the material specification requirements.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Universal Testing Machine | 600kN | UTM-1 | 08.05.2023 | 2022/51946/02 Dt.14.05.2022 | Yes |  | Yes
2 | Vernier Caliper | 0 to 300 mm | T-11 | 22.10.2023 | 8445/N/2022 Dtd.22.10.2022 | Yes |  | No
3 | PMI Machine | - | 500N8274 | 08.06.2023 | 500N8274 Dtd.08.06.2022 |  | Yes
4 | Hardness Testing Machine | - | 06/09/043 | 18.03.2023 | 22030621 Dtd.19.03.2023 | Yes
5 | M16 x 2P GO / NOGO | M16 x 2P | S9 / S10 | 05.06.2023 | 21.06.77337 Dtd.05.06.2021 | Yes

## Areas of concerns
Areas Of Concern
Photography not allowed by the Vendor ­ Client to note.
Client Email Dtd.15.03.2023 regarding confrimation on NDE (10% witness instead of 100% as per ITP)

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
None
Identification of Inspected Item(s):
20% randomly selected & Inspected fasteners hard stamped on the face as " " & the remaining quantity identified with soft stamp as on the tags attached with gunny bags/boxes
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable
IRN can be issued for PO Item numbers:
Expenses:
Remarks: