## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number | 8119276927
Notification Number | Email Date 20.12.2022
Project Name & Location | TAC S1 G3/1098
Client Name | Thermax Limited
End User Name | Thermax Limited
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name | REMI ELDELSTAHL TUBULARS LTD
PO Number (Client PO on Vendor) | 632948 DATE: 21.06.2022
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Boisar
Inspection Date(s) | 26.12.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | TU3F829H65000001-00 | Tube, SA 789 S32205, OD 19 mm X Thk 1.36 mm, EN 10204 3.2, CDS, ECT & Hydro Test as per Code, 6152 mm Long, Plain, Heat No : 225243, MTC No: 2205/T-001 Date 26.12.2022 | number | 1440 | 1440 | 1440 | 1440 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | NA | NA | NA
2 | QAP/ITP/QCP | NA | RETL/INSP/QAP/037-22-23 R01 | Approved by Thermax
3 | Drawing(s) | NA | NA | NA
4 | Procedure(s) | NA | NA | NA
5 | Datasheet(s) | NA | NA | NA
6 | Others (Specify) | NA | NA | NA

## Stages Witnessed
Stages Witnessed
QAP Stage No 3.2: Witnessed Tensile Test, Hardness, Flattening & Flaring on Tube Sample Drawn for Testing in a IN-House Lab as per specification -found satisfactory.
QAP Stage No 3.3: Witnessed Gain Size report, Microstructure report & Corrosion Test report as per A923 method Con Tube Sample one per Heat per size - found in order.
QAP Stage No 3.4: Witnessed Hydro Static Test of 10% of Tubes from offered lot at hydrostatic pressure of 1000 psi(g) for holding period of 10 seconds, No Leakage & No pressure drop observed during holding period- found satisfactory.
QAP Stage No 3.4: Witnessed Pneumcatic Test (Air Underwater Tes) of 10% of Tubes from offered lot at pneumatic pressure of 10.5 kg/cm2i(g) for holding period of 10 seconds, No Leakage & No pressure drop observed during holding period- found satisfactory.
QAP Stage No 3.5: Witnessed Eddy Current of 10% of Tubes from offered lot as per E 426 & A 1016 - found satisfactory.
QAP Stage No 3.6: Visual Inspection carried out of 10% of Tubes from offered lot for finsig/condition & workmanship- found satisfactory.
QAP Stage No 3.6: Witnessed Dimensional Inspection of 10% of Tubes from offered lot as per A789 & A1016 - found satisfactory.
QAP Stage No 3.7: Verified Marking of 10% of Tubes from offered lot as per A789 & A1016- found satisfactory.
QAP Stage No 4.1: Verified Packing of Tubes in Wooden Box with Inside Polythene Wrapping as per approved QAP- found satisfactory.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP Stage No 1.1: Reviewed Raw Material Test Certificate of Tube as per specification- found satisfactory.
QAP Stage No 2.2: Reviewed Heat Treatment Chart (Solution Annealing) of Tubes as per specification - found in order.
QAP Stage No 3.1: Reviewed Product Analysis Report of Tube for One Sample/Heat as per specification- found in order.
QAP Stage No 3.4: Reviewed Internal Hydro Test Report for 100% Qty as per specification - found in order.
QAP Stage No 3.4: Reviewed Internal Pneumatic Test Report for 100% Qty as per specification - found in order.
QAP Stage No 3.5 :Reviewed Internal Eddy Current Test Report for 100% Qty as per specification - found in order.
QAP Stage No 3.6: Reviewed Internal Visual & Dimensional Inspection Report for 100% Qty as per specification - found in order.
QAP Stage No 3.7: Reviewed Internal Veriifcation of Marking Report for 100% Qty as per specification - found in order.
QAP Stage No 5.1: Reviewed Vendor declared MTC (EN 10204 Type 3.2, MTC No 2205/T-001 Date 26.12.2022) as per approved QAP & Specification - found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
Yes
No

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
10 % Witnessed Tube double elctro eatched as “ ” near marking for Identification & Balance Tubes no stamping.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable subjected to pending activities mentioned below.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: