## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number | 010101031121/6
SAP number | 8118863250
Notification Number | As Per Email Dtd.15.01.2022
Project Name & Location | Laying and construction of steel gas pipeline and associated facilities for connectivity of ONGC Madanam field to Gail's Cauvery basin network at sv-2 Memathur (24" NB x 29 km) under Madanam to Memathur pipeline project
Client Name | M/s. Fire Safe Technologies LLP (FST)
End User Name | M/s. GAIL (INDIA) LIMITED
DEC / PMC / EPC Name | M/s. Mecon Limited & M/s. Tolani Projects Private Limited (TPPL), Gujarat
DEC / PMC / EPC Number | Not Applicable
Vendor Name | M/s. Fire Safe Technologies LLP (FST)
PO Number (Client PO on Vendor) | GAIL/MMPL/FIRE-FIGHTING-EQPT/001 Dtd.12.10.2021
Sub Vendor | Not Applicable
PO Number (Vendor PO on Sub Vendor) | Not Applicable
Inspection Location | M/s. Fire Safe Technologies LLP (FST), Plot No. EL-29, TTC Industrial Area, Behind Nelco, Mahape, Navi Mumbai – 400701
Inspection Date(s) | 2022-01-17

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1.1 | AK01010 | Electrical Siren ( 1 Km range) IS:1941-1976-RA2002 (Part 1), Make: JayKay | number | 2 | 2 | 2 | 2 | number
1.2 | AK01020 | Hand operated siren IS-6194-1971 RA- 2006, Make: Qutak Security Devices | number | 2 | 2 | 2 | 2 | meter
1.3 | AK01030 | Safety Helmet with GAIL LOGO - IS-2925-1984 RA2000, Make: Udyogi | number | 10 | 10 | 10 | 10 | km
1.5 | AK01050 | Rubber Hand Gloves Pair IS-4770 –1991 RA-2001, Make: Jyot | number | 10 | 10 | 10 | 10 | meter (number)
1.6 | AK01060 | Safety Torch, Make: FCG | number | 4 | 4 | 4 | 4 | km (number)
1.8 | AK01080 | Ear Muff, Make: Udyogi | number | 10 | 10 | 10 | 10 | each
1.9 | AK01090 | Ear Plug, Make: Udyogi (3M) | number | 10 | 10 | 10 | 10 | Piece
1.11 | AK01011 | Cotton Hand Gloves Pair, Make: Udyogi | number | 10 | 10 | 10 | 10 | Test sample
1.12 | AK01012 | Stretcher with Blanket as per IS:4037 : 1967 Ra-2001, Make: Udyogi | number | 2 | 2 | 2 | 2 | AU - All Unit
1.18 | AK01018 | Low Temperature Hand Gloves Pair, Make: Cold Plus | number | 4 | 4 | 4 | 4 | lot
1.19 | AK01019 | Resuscitator-IS-6194-1971 RA- 2006, Make: Jindal | number | 2 | 2 | 2 | 2 | Set
1.21 | AK01021 | Water Gel Blanket, Make: Agni Kavach Brand Modern Appareals | number | 2 | 2 | 2 | 2 | Running Meter
1.22 | AK01022 | Portable Gas Detectors, Make: Honeywell | number | 2 | 2 | 2 | 2 | kg
1.23 | AK01023 | Explosive Meter, Make: Honeywell | number | 2 | 2 | 2 | 2 | metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | FST-GAIL(M)-TOL-ITP-01 Rev.0 Dtd.14/10/2021 | Not Applicable | Approved By MECON Ltd.
3 | Drawing(s) | Not Applicable | Not Applicable | Not Applicable
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | FST-GAIL(M)-TOL-TDS-01 Rev.0, FST-GAIL(M)-TOL-TDS-02 Rev.0, FST-GAIL(M)-TOL-TDS-03 Rev.0, FST-GAIL(M)-TOL-TDS-05 Rev.0, FST-GAIL(M)-TOL-TDS-06 Rev.0, FST-GAIL(M)-TOL-TDS-08 Rev.0, FST-GAIL(M)-TOL-TDS-09 Rev.0, FST-GAIL(M)-TOL-TDS-11 Rev.0, FST-GAIL(M)-TOL-TDS-12 Rev.0, FST-GAIL(M)-TOL-TDS-15 Rev.0, FST-GAIL(M)-TOL-TDS-17 Rev.0, FST-GAIL(M)-TOL-TDS-18 Rev.0, FST-GAIL(M)-TOL-TDS-19 Rev.0 & FST-GAIL(M)-TOL-TDS-20 Rev.0. | Not Applicable | Approved By MECON Ltd.
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
ITP Clause no. A.1, A.2, A.3, A.5, A.6, A.8, A.9, A.11, A.12, A.14, A.17, A18 & A.19: Witnessed visual Inspection, make & marking verification for 10% qty. of randomly selected items from offered P.O. line items and found to meet approved datasheet & P.O. requirements.
ITP Clause no. A.1, A.2, A.6, A18 & A.19: Witnessed functional test (as applicable) on 10% qty. randomly selected items from offered P.O. line items and found to meet approved datasheet & P.O. requirements.
ITP Clause no. A.12: Witnessed dimensional Inspection (as applicable) on 10% qty. randomly selected items from offered P.O. line items and found to meet approved datasheet & P.O. requirements.

## Document reviewed
Document reviewed
Reviewed Internal test reports, test certificates / Atex & PESO certificates as submitted & declared by vendor for offered items and found to meet approved datasheet requirements.
Calibration certificate for measuring instruments used during inspection was reviewed and found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Measuring Tape | 0-5 M | SE/8606/2 | 2022-01-21 | SE/8606/2/0946 Dtd.22-01-2021 | Yes |  | Yes
No

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
None.
Identification of Inspected Item(s):
10% Inspected qty. provisionally affixed with hard stamp sticker as & remaining qty. with single hard stamp sticker on it.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable
IRN can be issued for PO Item numbers:
Expenses:
Remarks: