## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number | 8119020025
Notification Number | Email Dated 17.12.2022
Project Name & Location | 1.0 MTPA ALUMINA REFINERY STREAM 5
Client Name | M/s. Outotec India Private Limited
End User Name | M/s. NALCO
DEC / PMC / EPC Name | NA
DEC / PMC / EPC Number | NA
Vendor Name | M/s. REMI PROCESS PLANT & MACHINERY LIMITED
PO Number (Client PO on Vendor) | 3500033278 - 29/11/2021
Sub Vendor | NA
PO Number (Vendor PO on Sub Vendor) | NA
Inspection Location | Palghar
Inspection Date(s) | 20.12.2022

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
30 | CAT3130 | Agitator for Sump (09AG-5180) | Piece | 1 | 1 | 1 | 1 | number
40 | CAT3130 | Agitator for Sump (09AG-5181/5182) | Piece | 2 | 2 | 2 | 2 | meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | NA | NA | NA
2 | QAP/ITP/QCP | NA | QAP/21-OT-035 R01 Dated 31.01.2022 | Reviewed & Approved by TUV India in Vode AP & Approved by Outec India email Dated 18.02.2022
3 | Drawing(s) | NA | ATE-15380-12 R01 & ATE-15381-12 R01 | Approved by Outotec India
4 | Procedure(s) | NA | NA | NA
5 | Datasheet(s) | NA | NA | NA
6 | Others (Specify) | NA | NA | NA

## Stages Witnessed
Stages Witnessed
QAP CL No 2.4: Random Witness LPT of Weld Joint of impeller as per ASME Sec VIII Div I, Appendix 8- found satisfactory.
QAP CL No 3.1: Witnessed Impeller balancing In-Situ as per approved QAP- found satisfactory.
QAP CL No 3.2: Visual Inspection carried out of Agitator Assembly for finish, condition & workmanship- found satisfactory.
QAP CL No 3.2: Witnessed Overall Dimension check of Agitator for shaft , impeller & complete assembly as per approved drawing - found satisfactory.
QAP CL No 3.2: Witnessed Agitator No Load running trial test for 1 hrs as per approved QAP & Drg, checked Shaft RPM/Temp rise in motor, Gear Box & Bearing,/current drawn by motor in load/vibration/Noise/ Shaft Run out at free end:- found satisfactory.
QAP CL No 4: Visual Inspection carried out of Agitator after Painting for workmanship/finish- found satisfactory.
QAP CL No 4: Random Witnessed Paint Shade & DFT as per approved drawing - found satisfactory.
All measuring instruments/ equipment were verified for continued suitability for intended use, proper identification, calibration status, traceability to national standards & found satisfactory.

## Document reviewed
Document reviewed
QAP CL No 1.1: Reviewed MTC/Lab TC of Agitator Top Shaft, Bottom Shaft, Impeller Blade & Impeller Boss along with Ut Report of Shaft as per specification - found in order.
QAP CL No 1.2: Reviewed Gear Box MTC as per approved drawing - found in order.
QAP CL No 1.3: Reviewed MTC/Lab TC of Agitator Flange Coupling as per specification - found in order.
QAP CL No 2.1: Reviewed Shaft Dimension report as per approved drawing- found in order.
QAP CL No 2.3: Reviewed Impeller Dimension report as per approved drawing- found in order.
QAP CL No 2.2: Reviewed WPS/PQR as per ASME Sec IX - found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Magnetic DFT Gauge | 50-800 microns | 10142 | 25.04.2023 | TML/2022/04/04871 Dated 26.04.2022 | Yes |  | Yes
No

## Areas of concerns
Areas Of Concern
NIL

## Pending Activities
Pending Activities from this visit
NIL

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Identification of Inspected Item(s):
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
Acceptable.
IRN can be issued for PO Item numbers:
Expenses:
Remarks: