## Notes
Notes:
Data filled in General and conclusion Sections will not upload in TIIMES. Please use these sections to keep data ready for copy paste.
Data in Item Description columns of Accepted Quantity and cumulative Accepted quantity must be verified thoroughly before uploading in TIIMES.
Pending activity, Areas of concern & Details of measuring instruments sheets are applicable for IVR.
Select options from drop down list for unit of measurement (Item Description) & certifying body of measuring instruments (Details of measuring instruments).
Do not modify this format.
To start next row in cell itself use below shortcut: press 'alt + Enter' keys together. Alt + Enter

## General
Note: - Data filled in this sheet will not upload in TIIMES
Title | Details
Control Number
SAP number
Notification Number | As Per Email Dtd.09.10.2023
Project Name & Location | 1.2 MM TPA PTA Project IOCL Paradip
Client Name | M/s. Lloyd Insulations (India ) Limited
End User Name | M/s. IOCL - Paradeep
DEC / PMC / EPC Name | Technip Energies
DEC / PMC / EPC Number | N.A.
Vendor Name | Angels Aluminium Corporation
PO Number (Client PO on Vendor) | 288/240485863 Dtd.18/08/2022
Sub Vendor | M/s. Angels Aluminium Corporation
PO Number (Vendor PO on Sub Vendor) | 9000013050 Dtd.30/08/2023
Inspection Location | Angels Aluminium Corporation, Plot No. 14. Dewan Industrial Estate, Opp. old Bank of Maharashtra Near Palghar Plywood, Village Aliyali, Palghar -West. District: Palghar - 401404
Inspection Date(s) | 2023-10-10

## Item Description
Po Item No. | Item Code | Item Description | Unit | Po Quantity | Offered Quantity | Accepted Quantity (Please verify thouroghly before using this Column for IRN) | Cumulative Accepted Quanitity (for IRN Only)
1 | 12005078 | Aluminium Coil With Coating Of AL foil & Polyethylene AL Coil Make: BALCO, AL Coil MOC: IS 737 Alloy 31000 H3, Al. Coil Size:- 1 MM Thk. X 1219 MM Width, Total Coil Qty.: - 2 Nos., Balco Al. Coil Batch No.: - 4966802002 & 5995004001, AAC Coil No.: - 8529 & 8533, AAC Packet No.: - AAC10681 & AAC10682. Net Weight Of Coil: - 2308 Kgs. & 2360 Kgs. | kg | 40000 | 4668 | 4668 | 4668 | number
meter
km
meter (number)
km (number)
each
Piece
Test sample
AU - All Unit
lot
Set
Running Meter
kg
metric ton (tonne)
ton
cubic millimetre
cubic centimeter
cubic meter
cubic inch
cubic foot
mm
cm
in
foot
mile
yard
liter
kl
cl
ml
g
lb
oz
Sq. mm
Sq. cm
Sq. meter
Sq. in
Sq. foot

## Reference Documents
Sr. No. | Document Name | Client Document Number | Vendor Document Number | Approval Status
1 | PR/MR/ARM | Not Applicable | Not Applicable | Not Applicable
2 | QAP/ITP/QCP | T.EN./LLOYD/QAP/001 | Not Applicable | Approved By Client & Technip Energies
3 | Drawing(s) | Not Applicable | Not Applicable | Not Applicable
4 | Procedure(s) | Not Applicable | Not Applicable | Not Applicable
5 | Datasheet(s) | Not Applicable | Not Applicable | Not Applicable
6 | Others (Specify) | Not Applicable | Not Applicable | Not Applicable

## Stages Witnessed
Stages Witnessed
As per P.O. & approved QAP requirements, Inspection activities for offered aluminium coils with coating of AL foil & Polyethylene was carried out and observations found are as follows,
QAP Clause No. 1: Visual & dimensional Inspection of offered bare aluminium coils was witnessed and found free from injurious surface defects at the time of inspection.
QAP Clause No. 1: Dimensional Inspection of offered bare aluminium coils was witnessed and dimensions found to meet P.O., offer list & MTC requirements.
QAP Clause No. 2: Final visual Inspection for offered aluminium coils with coating of AL foil & Polyethylene was witnessed and found free from injurious surface defects at the time of inspection.
QAP Clause No. 2: Thickness of coating material (i.e. AL foil with polyethylene) was checked with digital micrometer and thickness found ~0.08 mm thk at the time of Inspection.
QAP Clause No. 3: Final dimensional inspection for offered aluminium coils with coating of AL foil & Polyethylene was witnessed to check width & total coil thickness with coating and dimensions found to meet the PO & packing list requirements.
QAP Clause No. 3: Packing & Marking Verification Witnessed for offered coils as per packing list and found in order.

## Document reviewed
Document reviewed
QAP Clause No.1: Material test certificate for plain aluminium coils as submitted & declared by vendor for offered lot was reviewed and found to meet relevant material specification requirements.
QAP Clause No. 2: Material test report for coating material (i.e. AL foil with polyethylene) as declared & submitted by vendor was reviewed and noted for record.
Packing detail list for offered coils as submitted & declared by vendor was reviewed and found in order.
Calibration certificates for measuring instruments used during inspection was reviewed and found in order.

## Details of measuring instrument
Sr. No. | Detail of Equipment(s) / Instrument(s) | Range | ID | Validity till Date | Calibration Certificate Number | NABL / OTHER CERT. BODIES / NABL Traceability (type Yes wherever applicable) | NON-NABL (type Yes wherever applicable)
1 | Digital Micrometer | 0-25 mm | 47120066 | 2024-02-21 | 23/1985 Dtd.22/02/2023 | Yes |  | Yes
2 | Measuring Tape | 0-5000 mm | AAC-MT-02 | 2024-02-21 | 23/1984 Dtd.22/02/2023 | Yes |  | No

## Areas of concerns
Areas Of Concern

## Pending Activities
Pending Activities from this visit

## Conclusion
Note: Data filled in this sheet will not upload in TIIMES
Non Conformities raised / Discrepancies observed during Inspection (If Any, Mention TUV India NCR Number ):
Nil
Identification of Inspected Item(s):
Inspected coils provisionally affixed with double soft stamp sticker as "TUV-968" near manufacturer's shipping mark details.
Conclusion (Acceptable / Not Acceptable / Acceptance subject to):
IRN can be issued for PO Item numbers:
Expenses:
Remarks: